## Definition
Name | Parameter | Value | Note
tfabDC | Days to fabricate 3 set of DC | 10 | Including DC wafer being shipped to Cornell
tfabMMB | Days to fabricate resonators/RF/RF cap for 3 MMB | 10 | uMUX and RF/cap fabrication decoupled from DC wafers, the day count does not include shipping days
tvalres | Days to screen resonators and shipping of resonators/RF/RF cap | 5 | Screening time + shipment to Princeton
tbondMMB | Days to bond 1 MMB | 3
tassMMB | Days to assemble 6 sets MMBs | 20 | Assuming 1MMB 1d:gluing/assem, 3d:bonding, 1d:gluing/assem; during the bonding of MMB, the next one can be started; so for getting 6 MMBs done, need 20 days; continuity check included
tvalMMB | Days to test 3 MMBs | 15 | Including shipping time, mounting, cooldown, warmup, open-up -> ready for next cool-down
NISTbatch | NIST batch size | 4 | Typically it is 3 arrays, but if there is single pixel, this can happen in the 4th batch
tfabNIST | Days to fabricate NIST batch | 30 | Including shipping to Princeton
tassNIST | Days to assemble NIST UFM | 6 | Assuming 1 NIST UFM 1d: assem, 2d: bonding, 1d:close-up
UCBbatch | UCB batch size | 6
tfabUCB | Days to fabrication UCB batch | 50
tassUCB | Days to assemble UCB UFM | 7 | Assuming 1 UCB UFM 1d:shipping MMB, 1d: assem, 2d: bonding, 1d:close-up
tvalUFM | Days to test 3 UFMs | 30 | Including shipping time, mounting, cooldown, warmup, open-up -> ready for next cool-down
tassSP | Days to assmble single pix | 3
tvalSP | Days to test single pix | 17 | Including shipping to Cornell
tvalOPT | Days for optical test 1 UFM | 30 | Including shipping to UCSD
tvalDC | Days to screen DC wafers | 10 | Including shipping tested DC to Princeton
*Assuming all the mechnical parts are ready to be used. Also assuming horns and lenslets are ready.
DR1 |  | P | Pton fridge
DR2 |  | O | Mich fridge
DR3 |  | G | Cornell fridge 1
DR4 |  | 6 | Cornell fridge 2
PTONLBASS |  | K
PTONSBASS |  | 5
UCBASS |  | 3
UCSD |  | R
NIST
UCB |  | 2
Lenslet |  | 1
NOTES: on 25 March, 2019, combined what was previouls called "SO-WBS-1.5-Local-Gantt-Chart" with this spreadsheet. The contents of "Local" are nw in the "R&D-Gantt" tab. Also renamed the original "GanttChart" sheet from this workbook to be called "GanttChart-v0" and renamed "GanttChart-v1" to "Master-Gantt" .
VERSION CHANGES:
2019-03-25 | Added 5 days for PRRs on R&D Gantt (was 1 day) | STS
2019-03-25 | Tied PRRs in Master-Gantt to lines from R&D Gantt | STS

## Master-Gantt
|  |  |  | Gantt Chart | [9 empty] | © 2006-2017 Vertex42.com |  |  | [Hide this row]
WBS 1.5 Gantt Chart for Detector & Readout Production & Validation, Simons Observatory
|  |  |  | Project Lead: Suzanne Staggs |  | Editor: Patty Ho
|  |  |  | Start: | 2018-11-19 | [12 empty] | Display: | Monthly
|  |  |  | End: | 2020-12-14 | [12 empty] | Month: | 1
|  |  |  | Today: | 2019-03-25 | [17 empty] | [42] | time axis 2018-11-01 to 2023-02-25
|  |  | WBS Level | WBS | Task | Note | Total Counts | Predecessors |  |  |  | Actual Start | Actual End | Work Days | Cal Days | % Done | Color | Actual Start | Actual End | Work Days | Cal Days | Days Done | Days Left | Planned Start | Planned End |  | 2018-11-01: 2018-11-01; 2018-12-01: 2018-12-01; 2019-01-01: 2019-01-01; 2019-02-01: 2019-02-01; 2019-03-01: 2019-03-01; 2019-04-01: 2019-04-01; 2019-05-01: 2019-05-01; 2019-06-01: 2019-06-01; 2019-07-01: 2019-07-01; 2019-08-01: 2019-08-01; 2019-09-01: 2019-09-01; 2019-10-01: 2019-10-01; 2019-11-01: 2019-11-01; 2019-12-01: 2019-12-01; 2020-01-01: 2020-01-01; 2020-02-01: 2020-02-01; 2020-03-01: 2020-03-01; 2020-04-01: 2020-04-01; 2020-05-01: 2020-05-01; 2020-06-01: 2020-06-01; 2020-07-01: 2020-07-01; 2020-08-01: 2020-08-01; 2020-09-01: 2020-09-01; 2020-10-01: 2020-10-01; 2020-11-01: 2020-11-01; 2020-12-01: 2020-12-01; 2021-01-01: 2021-01-01; 2021-02-01: 2021-02-01; 2021-03-01: 2021-03-01; 2021-04-01: 2021-04-01; 2021-05-01: 2021-05-01; 2021-06-01: 2021-06-01; 2021-07-01: 2021-07-01; 2021-08-01: 2021-08-01; 2021-09-01: 2021-09-01; 2021-10-01: 2021-10-01; 2021-11-01: 2021-11-01; 2021-12-01: 2021-12-01; 2022-01-01: 2022-01-01; 2022-02-01: 2022-02-01; 2022-03-01: 2022-03-01; 2022-04-01: 2022-04-01; 2022-05-01: 2022-05-01; 2022-06-01: 2022-06-01; 2022-07-01: 2022-07-01; 2022-08-01: 2022-08-01; 2022-09-01: 2022-09-01; 2022-10-01: 2022-10-01; 2022-11-01: 2022-11-01; 2022-12-01: 2022-12-01; 2023-01-01: 2023-01-01; 2023-02-01: 2023-02-01
[27 empty] | 2018-11-01 | [6 empty] | 2018-12-01 | [6 empty] | 2019-01-01 | [6 empty] | 2019-02-01 | [6 empty] | 2019-03-01 | [6 empty] | 2019-04-01 | [6 empty] | 2019-05-01 | [6 empty] | 2019-06-01 | [6 empty] | 2019-07-01 | [6 empty] | 2019-08-01 | [6 empty] | 2019-09-01 | [6 empty] | 2019-10-01 | [6 empty] | 2019-11-01 | [6 empty] | 2019-12-01 | [6 empty] | 2020-01-01 | [6 empty] | 2020-02-01 | [6 empty] | 2020-03-01 | [6 empty] | 2020-04-01 | [6 empty] | 2020-05-01 | [6 empty] | 2020-06-01 | [6 empty] | 2020-07-01 | [6 empty] | 2020-08-01 | [6 empty] | 2020-09-01 | [6 empty] | 2020-10-01 | [6 empty] | 2020-11-01 | [6 empty] | 2020-12-01 | [6 empty] | 2021-01-01 | [6 empty] | 2021-02-01 | [6 empty] | 2021-03-01 | [6 empty] | 2021-04-01 | [6 empty] | 2021-05-01 | [6 empty] | 2021-06-01 | [6 empty] | 2021-07-01 | [6 empty] | 2021-08-01 | [6 empty] | 2021-09-01 | [6 empty] | 2021-10-01 | [6 empty] | 2021-11-01 | [6 empty] | 2021-12-01 | [6 empty] | 2022-01-01 | [6 empty] | 2022-02-01 | [6 empty] | 2022-03-01 | [6 empty] | 2022-04-01 | [6 empty] | 2022-05-01 | [6 empty] | 2022-06-01 | [6 empty] | 2022-07-01 | [6 empty] | 2022-08-01 | [6 empty] | 2022-09-01 | [6 empty] | 2022-10-01 | [6 empty] | 2022-11-01 | [6 empty] | 2022-12-01 | [6 empty] | 2023-01-01 | [6 empty] | 2023-02-01
Name | Parameter | Value | [24 empty] | 2018-11-01: 1; 2018-12-01: 2; 2019-01-01: 3; 2019-02-01: 4; 2019-03-01: 5; 2019-04-01: 6; 2019-05-01: 7; 2019-06-01: 8; 2019-07-01: 9; 2019-08-01: 10; 2019-09-01: 11; 2019-10-01: 12; 2019-11-01: 13; 2019-12-01: 14; 2020-01-01: 15; 2020-02-01: 16; 2020-03-01: 17; 2020-04-01: 18; 2020-05-01: 19; 2020-06-01: 20; 2020-07-01: 21; 2020-08-01: 22; 2020-09-01: 23; 2020-10-01: 24; 2020-11-01: 25; 2020-12-01: 26; 2021-01-01: 27; 2021-02-01: 28; 2021-03-01: 29; 2021-04-01: 30; 2021-05-01: 31; 2021-06-01: 32; 2021-07-01: 33; 2021-08-01: 34; 2021-09-01: 35; 2021-10-01: 36; 2021-11-01: 37; 2021-12-01: 38; 2022-01-01: 39; 2022-02-01: 40; 2022-03-01: 41; 2022-04-01: 42; 2022-05-01: 43; 2022-06-01: 44; 2022-07-01: 45; 2022-08-01: 46; 2022-09-01: 47; 2022-10-01: 48; 2022-11-01: 49; 2022-12-01: 50; 2023-01-01: 51; 2023-02-01: 52
tfabDC | Days to fabricate 3 set of DC | 10 | 1 | 1 | (WBS 1.5) | [ name ] | [11 empty] | - | - | - | - | - | - |  |  | I12<>"",J12<>"",K12<>"",L12<>""
tfabMUX | Days to fabricate/screen/ship resonators for 2 MMBs | 14 | 2 | 1.1 | Readout PRR |  |  | 3.57 |  |  |  | 2019-05-07 |  | 1 |  |  |  | 2019-05-07 | 2019-05-07 | 1 | 1 | 0 | 1
tfabRF | Days to fabricate RF for 3 MMB | 5 | 2 | 1.2 | NIST fab 3 sets of MMBs | [6 empty] | 2019-05-08 | 2019-05-21 | 10 |  |  |  | 2019-05-08 | 2019-05-21
tbondMMB | Days to bond 1 MMB | 3 | 3 | 1.2.1 | Fabrication 3 sets DC(A1-A3) |  |  | 1.1 | [5 empty] | 10 |  |  |  | 2019-05-08 | 2019-05-21
tassMMB | Days to assemble 6 sets MMBs | 34 | 3 | 1.2.2 | Fabrication/screen/ship 2 sets resonators(A1-A2) |  |  | 1.1 | [5 empty] | 14 |  |  |  | 2019-05-08 | 2019-05-28
tvalMMB | Days to test 3 MMBs | 15 | 3 | 1.2.3 | Fabrication/screen/ship 2 sets resonators(A3-B1) |  |  | 1.2.2 | [5 empty] | 14 |  |  |  | 2019-05-29 | 2019-06-17
NISTbatch | NIST batch size | 4 | 3 | 1.2.4 | Fabrication 3 sets RF/cap (A1-A3) |  |  | 1.1 | [5 empty] | 10 |  |  |  | 2019-05-08 | 2019-05-21
tfabNIST | Days to fabricate NIST batch | 30 | 2 | 1.3 | Screen DC wafers (A1-A3) in DR3 |  |  | 1.1 | [5 empty] | 15 |  |  | o | 2019-05-08 | 2019-05-29
tassNIST | Days to assemble NIST UFM | 6 | 2 | 1.4 | Assemble 3 MMBs (A1-A3) | Lbonder |  | 1.2.4 | 1.3 | 1.2.2 |  |  |  | 19 |  |  | k | 2019-05-30 | 2019-06-25
UCBbatch | UCB batch size | 6 | 2 | 1.5 | Test 3 MMBs (A1-A3) in DR1 |  | 3 MMBs | 1.4 | [5 empty] | 15 |  |  | p | 2019-06-26 | 2019-07-17
tfabUCB | Days to fabrication UCB batch | 50 | 2 | 1.6 | NIST fab 6 sets of MMBs | [6 empty] | 2019-05-22 | 2019-06-19 | 10 |  |  |  | 2019-05-22 | 2019-06-19
tassUCB | Days to assemble UCB UFM | 7 | 3 | 1.6.1 | Fabrication 3 sets DC(B1-B3) |  |  | 1.2.1 | [5 empty] | 10 |  |  |  | 2019-05-22 | 2019-06-05
tvalUFM | Days to test 3 UFMs | 30 | 3 | 1.6.2 | Fabrication/screen/ship 2 sets resonators(B2-B3) |  |  | 1.2.3 | [5 empty] | 14 |  |  |  | 2019-06-18 | 2019-07-08
tassSP | Days to assmble single pix | 3 | 3 | 1.6.3 | Fabrication/screen/ship 2 sets resonators(B4-B5) |  |  | 1.6.2 | [5 empty] | 14 |  |  |  | 2019-07-09 | 2019-07-26
tvalSP | Days to test single pix | 17 | 3 | 1.6.4 | Fabrication/screen/ship 2 sets resonators(B6-C1) |  |  | 1.6.3 | [5 empty] | 14 |  |  |  | 2019-07-29 | 2019-08-16
tvalOPT | Days for optical test 1 UFM | 30 | 3 | 1.6.5 | Fabrication 3 sets RF/cap (B1-B3) |  |  | 1.2.4 | [5 empty] | 10 |  |  |  | 2019-05-22 | 2019-06-05
tvalDC | Days to screen DC wafers | 10 | 3 | 1.6.6 | Fabrication 3 sets RF/cap (B4-B6) |  |  | 1.6.5 | [5 empty] | 10 |  |  |  | 2019-06-06 | 2019-06-19
tfabLenslet | Days to fabricate 3 sets of lenslet | 40 | 3 | 1.6.7 | Fabrication 3 sets DC(B4-B6) |  |  | 1.6.1 | [5 empty] | 10 |  |  |  | 2019-06-06 | 2019-06-19
tfabHorn | Days to fabricate 3 sets of horn | 30 | 2 | 1.7 | Screen DC wafers (B1-B6) in DR3 |  |  | 1.6.6 | 1.3 |  |  |  |  | 10 |  |  | o | 2019-06-20 | 2019-07-03
|  |  | 2 | 1.8 | Assemble 6 MMBs (B1-B6) | Lbonder |  | 1.7 | 1.6.6 | 1.4 | 1.6.2 |  |  | 34 |  |  | k | 2019-07-09 | 2019-08-27
|  |  | 2 | 1.9 | Test 3 MMBs (B1-B3) in DR3 |  | 6 MMBs | 1.8 | 1.25 |  |  |  |  | 15 |  |  | o | 2019-09-04 | 2019-09-24
|  |  | 2 | 1.10 | Test 3 MMBs (B4-B6) in DR1 |  | 9 MMBs | 1.8 | 1.5 |  |  |  |  | 15 |  |  | p | 2019-08-28 | 2019-09-18
|  |  | 2 | 1.11 | NIST MF-h Detector PRR | [6 empty] | 2019-05-20 |  | 1 |  |  |  | 2019-05-20 | 2019-05-20
|  |  | 2 | 1.12 | NIST fabs 3 MF arrays + 1 single pixel |  |  | 1.11 | [5 empty] | 30 |  |  |  | 2019-05-21 | 2019-07-02
|  |  | 2 | 1.13 | Assemble single pixels | Sbonder |  | 1.12 | [5 empty] | 3 |  |  | 5 | 2019-07-03 | 2019-07-08
|  |  | 2 | 1.14 | Test single pixels in DR4 |  |  | 1.13 | [5 empty] | 17 |  |  | 6 | 2019-07-09 | 2019-07-31
|  |  | 2 | 1.15 | 3 MF horns fab/shipped to Princeton | [6 empty] | 2019-05-14 |  | 30 |  |  | 4 | 2019-05-14 | 2019-06-25
|  |  | 2 | 1.16 | Assemble 3 MF-h UFMs with A1-A3 | Sbonder |  | 1.12 | 1.13 | 1.15 |  |  |  | 6 |  |  | 5 | 2019-07-09 | 2019-07-16
|  |  | 2 | 1.17 | Test 3 MF-h UFMs in DR2 |  | 3 MF-h | 1.16 | [5 empty] | 30 |  |  | g | 2019-07-17 | 2019-08-29
|  |  | 2 | 1.18 | Test 1 of the above MF-h UFM @ UCSD |  |  | 1.17 | [5 empty] | 30 |  |  | r | 2019-08-30 | 2019-10-11
|  |  | 2 | 1.19 | NIST fab 6 sets of MMBs | [6 empty] | 2019-06-20 | 2019-07-18 | 10 |  |  |  | 2019-06-20 | 2019-07-18
|  |  | 3 | 1.19.1 | Fabrication 3 sets DC(C1-C3) |  |  | 1.6.7 | [5 empty] | 10 |  |  |  | 2019-06-20 | 2019-07-03
|  |  | 3 | 1.19.2 | Fabrication/screen/ship 2 sets resonators(C2-C3) |  |  | 1.6.4 | [5 empty] | 14 |  |  |  | 2019-08-19 | 2019-09-09
|  |  | 3 | 1.19.3 | Fabrication/screen/ship 2 sets resonators(C4-C5) |  |  | 1.19.2 | [5 empty] | 14 |  |  |  | 2019-09-10 | 2019-09-27
|  |  | 3 | 1.19.4 | Fabrication/screen/ship 2 sets resonators(C6-D1) |  |  | 1.19.3 | [5 empty] | 14 |  |  |  | 2019-09-30 | 2019-10-18
|  |  | 3 | 1.19.5 | Fabrication 3 sets RF/cap (C1-C3) |  |  | 1.6.6 | [5 empty] | 10 |  |  |  | 2019-06-20 | 2019-07-03
|  |  | 3 | 1.19.6 | Fabrication 3 sets RF/cap (C4-C6) |  |  | 1.19.5 | [5 empty] | 10 |  |  |  | 2019-07-05 | 2019-07-18
|  |  | 3 | 1.19.7 | Fabrication 3 sets DC(C4-C6) |  |  | 1.19.1 | [5 empty] | 10 |  |  |  | 2019-07-05 | 2019-07-18
|  |  | 2 | 1.20 | Screen DC wafers (C1-C6) in DR3 |  |  | 1.19.7 | 1.19.1 | 1.7 |  |  |  | 10 |  |  | o | 2019-07-19 | 2019-08-01
|  |  | 2 | 1.21 | Assemble 6 MMBs (C1-C6) | Lbonder |  | 1.20 | 1.8 | 1.19.2 | 1.19.6 |  |  | 34 |  |  | k | 2019-09-10 | 2019-10-28
|  |  | 2 | 1.22 | Test 3 MMBs (C1-C3) in DR1 |  | 12 MMBs | 1.21 | 1.10 |  |  |  |  | 15 |  |  | p | 2019-10-29 | 2019-11-19
|  |  | 2 | 1.23 | Test 3 MMBs (C4-C6) in DR3 |  | 15 MMBs | 1.21 | 1.9 | 1.51 |  |  |  | 15 |  |  | o | 2019-10-31 | 2019-11-21
|  |  | 2 | 1.24 | NIST fab 6 sets of MMBs | [6 empty] | 2019-07-19 | 2019-08-16 | 10 |  |  |  | 2019-07-19 | 2019-08-16
|  |  | 3 | 1.24.1 | Fabrication 3 sets DC(D1-D3) |  |  | 1.19.7 | [5 empty] | 10 |  |  |  | 2019-07-19 | 2019-08-01
|  |  | 3 | 1.24.2 | Fabrication/screen/ship 2 sets resonators(D2-D3) |  |  | 1.19.4 | [5 empty] | 14 |  |  |  | 2019-10-21 | 2019-11-07
|  |  | 3 | 1.24.3 | Fabrication/screen/ship 2 sets resonators(D4-D5) |  |  | 1.24.2 | [5 empty] | 14 |  |  |  | 2019-11-08 | 2019-11-29
|  |  | 3 | 1.24.4 | Fabrication/screen/ship 2 sets resonators(D6-E1) |  |  | 1.24.3 | [5 empty] | 14 |  |  |  | 2019-12-02 | 2019-12-19
|  |  | 3 | 1.24.5 | Fabrication 3 sets RF/cap (D1-D3) |  |  | 1.19.6 | [5 empty] | 10 |  |  |  | 2019-07-19 | 2019-08-01
|  |  | 3 | 1.24.6 | Fabrication 3 sets RF/cap (D4-D6) |  |  | 1.24.5 | [5 empty] | 10 |  |  |  | 2019-08-02 | 2019-08-16
|  |  | 3 | 1.24.7 | Fabrication 3 sets DC(D4-D6) |  |  | 1.24.1 | [5 empty] | 10 |  |  |  | 2019-08-02 | 2019-08-16
|  |  | 2 | 1.25 | Screen DC wafers (D1-D6) in DR3 |  |  | 1.24.7 | 1.24.1 | 1.20 |  |  |  | 10 |  |  | o | 2019-08-19 | 2019-09-03
|  |  | 2 | 1.26 | Assemble 6 MMBs (D1-D6) | Lbonder |  | 1.21 | 1.25 | 1.24.6 | 1.24.2 |  |  | 34 |  |  | k | 2019-11-08 | 2019-12-31
|  |  | 2 | 1.27 | Test 3 MMBs (D1-D3) in DR1 |  | 18 MMBs | 1.26 | 1.22 |  |  |  |  | 15 |  |  | p | 2020-01-02 | 2020-01-23
|  |  | 2 | 1.28 | Test 3 MMBs (D4-D6) in DR3 |  | 21 MMBs | 1.26 | 1.65 |  |  |  |  | 15 |  |  | o | 2020-01-02 | 2020-01-23
|  |  | 2 | 1.29 | NIST fab 6 sets of MMBs | [6 empty] | 2019-08-19 | 2019-09-17 | 10 |  |  |  | 2019-08-19 | 2019-09-17
|  |  | 3 | 1.29.1 | Fabrication 3 sets DC(E1-E3) |  |  | 1.24.7 | [5 empty] | 10 |  |  |  | 2019-08-19 | 2019-09-03
|  |  | 3 | 1.29.2 | Fabrication/screen/ship 2 sets resonators(E2-E3) |  |  | 1.24.4 | [5 empty] | 14 |  |  |  | 2019-12-20 | 2020-01-13
|  |  | 3 | 1.29.3 | Fabrication/screen/ship 2 sets resonators(E4-E5) |  |  | 1.29.2 | [5 empty] | 14 |  |  |  | 2020-01-14 | 2020-02-03
|  |  | 3 | 1.29.4 | Fabrication/screen/ship 2 sets resonators(E6-F1) |  |  | 1.29.3 | [5 empty] | 14 |  |  |  | 2020-02-04 | 2020-02-24
|  |  | 3 | 1.29.5 | Fabrication 3 sets RF/cap (E1-E3) |  |  | 1.24.6 | [5 empty] | 10 |  |  |  | 2019-08-19 | 2019-09-03
|  |  | 3 | 1.29.6 | Fabrication 3 sets RF/cap (E4-E6) |  |  | 1.29.5 | [5 empty] | 10 |  |  |  | 2019-09-04 | 2019-09-17
|  |  | 3 | 1.29.7 | Fabrication 3 sets DC(E4-E6) |  |  | 1.29.1 | [5 empty] | 10 |  |  |  | 2019-09-04 | 2019-09-17
|  |  | 2 | 1.30 | Screen DC wafers (E1-E6) in DR3 |  |  | 1.29.7 | 1.29.1 |  |  | 2019-09-04 | 2019-09-24 | 10 |  |  | o | 2019-09-04 | 2019-09-24
|  |  | 2 | 1.31 | Assemble 6 MMBs (E1-E6) | Lbonder |  | 1.26 | 1.30 | 1.29.6 | 1.29.2 |  |  | 34 |  |  | k | 2020-01-14 | 2020-03-03
|  |  | 2 | 1.32 | Test 3 MMBs (E1-E3) in DR1 |  | 24 MMBs | 1.31 | 1.27 |  |  |  |  | 15 |  |  | p | 2020-03-04 | 2020-03-24
|  |  | 2 | 1.33 | Test 3 MMBs (E4-E6) in DR2 |  | 27 MMBs | 1.31 | 1.96 |  |  |  |  | 15 |  |  | g | 2020-03-04 | 2020-03-24
|  |  | 2 | 1.34 | NIST fabs 3 arrays |  |  | 1.12 | [5 empty] | 30 |  |  |  | 2019-07-03 | 2019-08-15
|  |  | 2 | 1.35 | 3 MF horns fab/shipped to Princeton |  |  | 1.15 | [5 empty] | 30 |  |  | 4 | 2019-06-26 | 2019-08-08
|  |  | 2 | 1.36 | Assemble 3 UFM-hs w/ B1-B3 | Sbonder |  | 1.34 | 1.16 | 1.13 | 1.35 |  |  | 6 |  |  | 5 | 2019-08-16 | 2019-08-23
|  |  | 2 | 1.37 | Test 3 UFMs in DR2 |  | 6 MF-h | 1.36 | 1.17 |  |  |  |  | 30 |  |  | g | 2019-08-30 | 2019-10-11
|  |  | 2 | 1.38 | UCB Detector PRR | [6 empty] | 2019-06-06 |  | 1 |  |  |  | 2019-06-06 | 2019-06-06
|  |  | 2 | 1.39 | UCB fabs 6 arrays + 1 single pixel |  |  | 1.38 | [5 empty] | 50 |  |  | 2 | 2019-06-07 | 2019-08-19
|  |  | 2 | 1.40 | 3 sets of lenslet wafers fabricated |  |  | 1.38 | [5 empty] | 40 |  |  | 1 | 2019-06-07 | 2019-08-02
|  |  | 2 | 1.41 | Assemble single pixels | Sbonder |  | 1.39 | 1.36 |  |  |  |  | 3 |  |  | 5 | 2019-08-27 | 2019-08-29
|  |  | 2 | 1.42 | Test single pixels in DR4 |  |  | 1.41 | 1.14 |  |  |  |  | 17 |  |  | 6 | 2019-08-30 | 2019-09-24
|  |  | 2 | 1.43 | Assemble 3 UCB UFMs w/G1-G3 | Bbonder |  | 1.39 | 1.58 | 1.40 |  |  |  | 7 |  |  | 3 | 2020-07-03 | 2020-07-13
|  |  | 2 | 1.44 | Test 3 UFMs in DR1 |  | 3 MF-l | 1.43 | 1.22 |  |  |  |  | 30 |  |  | p | 2020-07-14 | 2020-08-25
|  |  | 2 | 1.45 | Test 1 of the above 3 UFM @ UCSD |  |  | 1.44 | 1.18 |  |  |  |  | 30 |  |  | r | 2020-08-26 | 2020-10-08
|  |  | 2 | 1.46 | 3 sets of lenslet wafers fabricated |  |  | 1.40 | [5 empty] | 40 |  |  | 2 | 2019-08-06 | 2019-10-02
|  |  | 2 | 1.47 | Assemble 3 UCB UFMs w/ G4-G6 | Bbonder |  | 1.43 | 1.59 | 1.39 | 1.46 |  |  | 7 |  |  | 3 | 2020-07-24 | 2020-08-04
|  |  | 2 | 1.48 | Test 3 UFMs in DR2 | LATR1 | 6 MF-l | 1.47 | 1.63 |  |  |  |  | 30 |  |  | g | 2020-08-05 | 2020-09-17
|  |  | 2 | 1.49 | Test 1 of the above 3 UFM @ UCSD |  |  | 1.45 | 1.48 |  |  |  |  | 30 |  |  | r | 2020-10-09 | 2020-11-23
|  |  | 2 | 1.50 | NIST fab 6 sets of MMBs | [6 empty] | 2019-09-18 | 2019-10-16 | 10 |  |  |  | 2019-09-18 | 2019-10-16
|  |  | 3 | 1.50.1 | Fabrication 3 sets DC(F1-F3) |  |  | 1.29.7 | [5 empty] | 10 |  |  |  | 2019-09-18 | 2019-10-01
|  |  | 3 | 1.50.2 | Fabrication/screen/ship 2 sets resonators(F2-F3) |  |  | 1.29.2 | [5 empty] | 14 |  |  |  | 2020-01-14 | 2020-02-03
|  |  | 3 | 1.50.3 | Fabrication/screen/ship 2 sets resonators(F4-F5) |  |  | 1.50.2 | [5 empty] | 14 |  |  |  | 2020-02-04 | 2020-02-24
|  |  | 3 | 1.50.4 | Fabrication/screen/ship 2 sets resonators(F6-G1) |  |  | 1.50.3 | [5 empty] | 14 |  |  |  | 2020-02-25 | 2020-03-13
|  |  | 3 | 1.50.5 | Fabrication 3 sets RF/cap (F1-F3) |  |  | 1.29.6 | [5 empty] | 10 |  |  |  | 2019-09-18 | 2019-10-01
|  |  | 3 | 1.50.6 | Fabrication 3 sets RF/cap (F4-F6) |  |  | 1.50.5 | [5 empty] | 10 |  |  |  | 2019-10-02 | 2019-10-16
|  |  | 3 | 1.50.7 | Fabrication 3 sets DC(F4-F6) |  |  | 1.50.1 | [5 empty] | 10 |  |  |  | 2019-10-02 | 2019-10-16
|  |  | 2 | 1.51 | Screen DC wafers (F1-F6) in DR3 |  |  | 1.50.7 | 1.50.1 | 1.30 |  |  |  | 10 |  |  | o | 2019-10-17 | 2019-10-30
|  |  | 2 | 1.52 | Assemble 6 MMBs (F1-F6) | Lbonder |  | 1.31 | 1.51 | 1.50.6 | 1.50.2 |  |  | 34 |  |  | k | 2020-03-04 | 2020-04-22
|  |  | 2 | 1.53 | Test 3 MMBs (F1-F3) in DR1 |  | 30 MMBs | 1.52 | 1.32 |  |  |  |  | 15 |  |  | p | 2020-04-23 | 2020-05-14
|  |  | 2 | 1.54 | Test 3 MMBs (F4-F6) in DR2 |  | 33 MMBs | 1.52 | 1.33 |  |  |  |  | 15 |  |  | g | 2020-04-23 | 2020-05-14
|  |  | 2 | 1.55 | NIST fab 6 sets of MMBs | [6 empty] | 2019-10-17 | 2019-11-14 | 10 |  |  |  | 2019-10-17 | 2019-11-14
|  |  | 3 | 1.55.1 | Fabrication 3 sets DC(G1-G3) |  |  | 1.50.7 | [5 empty] | 10 |  |  |  | 2019-10-17 | 2019-10-30
|  |  | 3 | 1.55.2 | Fabrication/screen/ship 2 sets resonators(G2-G3) |  |  | 1.50.4 | [5 empty] | 14 |  |  |  | 2020-03-16 | 2020-04-02
|  |  | 3 | 1.55.3 | Fabrication/screen/ship 2 sets resonators(G4-G5) |  |  | 1.55.2 | [5 empty] | 14 |  |  |  | 2020-04-03 | 2020-04-24
|  |  | 3 | 1.55.4 | Fabrication/screen/ship 2 sets resonators(G6-H1) |  |  | 1.55.3 | [5 empty] | 14 |  |  |  | 2020-04-27 | 2020-05-15
|  |  | 3 | 1.55.5 | Fabrication 3 sets RF/cap (G1-G3) |  |  | 1.50.6 | [5 empty] | 10 |  |  |  | 2019-10-17 | 2019-10-30
|  |  | 3 | 1.55.6 | Fabrication 3 sets RF/cap (G4-G6) |  |  | 1.55.5 | [5 empty] | 10 |  |  |  | 2019-10-31 | 2019-11-14
|  |  | 3 | 1.55.7 | Fabrication 3 sets DC(G4-G6) |  |  | 1.55.1 | [5 empty] | 10 |  |  |  | 2019-10-31 | 2019-11-14
|  |  | 2 | 1.56 | Screen DC wafers (G1-G6) in DR3 |  |  | 1.55.7 | 1.55.1 | 1.23 |  |  |  | 10 |  |  | o | 2019-11-22 | 2019-12-06
|  |  | 2 | 1.57 | Assemble 6 MMBs (G1-G6) | Lbonder |  | 1.52 | 1.56 | 1.55.6 | 1.55.2 |  |  | 34 |  |  | k | 2020-04-23 | 2020-06-11
|  |  | 2 | 1.58 | Test 3 MMBs (G1-G3) in DR3 |  | 36 MMBs | 1.57 |  | 1.110 |  |  |  | 15 |  |  | o | 2020-06-12 | 2020-07-02
|  |  | 2 | 1.59 | Test 3 MMBs (G4-G6) in DR3 |  | 39 MMBs | 1.57 |  | 1.58 |  |  |  | 15 |  |  | o | 2020-07-03 | 2020-07-23
|  |  | 2 | 1.60 | NIST fabs 3 arrays |  |  | 1.34 | [5 empty] | 30 |  |  |  | 2019-08-16 | 2019-09-30
|  |  | 2 | 1.61 | 3 MF horns fab/shipped to Princeton |  |  | 1.35 | [5 empty] | 30 |  |  | 4 | 2019-08-09 | 2019-09-23
|  |  | 2 | 1.62 | Assemble 3 UFMs w/ B4-B6 | Sbonder |  | 1.60 | 1.10 | 1.41 | 1.61 |  |  | 6 |  |  | 5 | 2019-10-01 | 2019-10-08
|  |  | 2 | 1.63 | Test 3 UFMs in DR2 | SAT1 | 9 MF-h | 1.62 | 1.37 |  |  |  |  | 30 |  |  | g | 2019-10-15 | 2019-11-26
|  |  | 2 | 1.64 | NIST fab 6 sets of MMBs | [6 empty] | 2019-11-15 | 2019-12-13 | 10 |  |  |  | 2019-11-15 | 2019-12-13
|  |  | 3 | 1.64.1 | Fabrication 3 sets DC(H1-H3) |  |  | 1.55.7 | [5 empty] | 10 |  |  |  | 2019-11-15 | 2019-11-29
|  |  | 3 | 1.64.2 | Fabrication/screen/ship 2 sets resonators(H2-H3) |  |  | 1.55.4 | [5 empty] | 14 |  |  |  | 2020-05-18 | 2020-06-05
|  |  | 3 | 1.64.3 | Fabrication/screen/ship 2 sets resonators(H4-H5) |  |  | 1.64.2 | [5 empty] | 14 |  |  |  | 2020-06-08 | 2020-06-25
|  |  | 3 | 1.64.4 | Fabrication/screen/ship 2 sets resonators(H6-I1) |  |  | 1.64.3 | [5 empty] | 14 |  |  |  | 2020-06-26 | 2020-07-15
|  |  | 3 | 1.64.5 | Fabrication 3 sets RF/cap (H1-H3) |  |  | 1.55.6 | [5 empty] | 10 |  |  |  | 2019-11-15 | 2019-11-29
|  |  | 3 | 1.64.6 | Fabrication 3 sets RF/cap (H4-H6) |  |  | 1.64.5 | [5 empty] | 10 |  |  |  | 2019-12-02 | 2019-12-13
|  |  | 3 | 1.64.7 | Fabrication 3 sets DC(H4-H6) |  |  | 1.64.1 | [5 empty] | 10 |  |  |  | 2019-12-02 | 2019-12-13
|  |  | 2 | 1.65 | Screen DC wafers (H1-H6) in DR3 |  |  | 1.64.7 | 1.64.1 | 1.56 |  |  |  | 10 |  |  | o | 2019-12-16 | 2019-12-31
|  |  | 2 | 1.66 | Assemble 6 MMBs (H1-H6) | Lbonder |  | 1.57 | 1.65 | 1.64.6 | 1.64.2 |  |  | 34 |  |  | k | 2020-06-12 | 2020-07-29
|  |  | 2 | 1.67 | Test 3 MMBs (H1-H3) in DR1 |  | 42 MMBs | 1.66 | 1.156 |  |  |  |  | 15 |  |  | p | 2020-09-29 | 2020-10-20
|  |  | 2 | 1.68 | Test 3 MMBs (H4-H6) in DR1 |  | 45 MMBs | 1.66 | 1.67 |  |  |  |  | 15 |  |  | p | 2020-10-21 | 2020-11-10
|  |  | 2 | 1.69 | UCB fabs 6 arrays |  |  | 1.39 | [5 empty] | 50 |  |  | 2 | 2019-08-20 | 2019-10-31
|  |  | 2 | 1.70 | 3 sets of lenslet wafers fabricated |  |  | 1.46 | [5 empty] | 40 |  |  | 1 | 2019-10-03 | 2019-12-02
|  |  | 2 | 1.71 | Assemble 3 UCB UFMs w/ H1-H3 | Bbonder |  | 1.69 | 1.67 | 1.47 | 1.70 |  |  | 7 |  |  | 3 | 2020-10-21 | 2020-10-29
|  |  | 2 | 1.72 | Test 3 UFMs in DR2 | LATR2 | 9 MF-l | 1.71 | 1.140 |  |  |  |  | 30 |  |  | g | 2020-12-29 | 2021-02-10
|  |  | 2 | 1.73 | 3 sets of lenslet wafers fabricated |  |  | 1.70 | [5 empty] | 40 |  |  | 1 | 2019-12-03 | 2020-01-31
|  |  | 2 | 1.74 | Assemble 3 UCB UFMs w/ H4-H6 | Bbonder |  | 1.71 | 1.68 | 1.69 | 1.73 |  |  | 7 |  |  | 3 | 2020-11-12 | 2020-11-20
|  |  | 2 | 1.75 | Test 3 UFMs in DR2 |  | 12 MF-l | 1.74 | 1.72 |  |  |  |  | 30 |  |  | g | 2021-02-11 | 2021-03-25
|  |  | 2 | 1.76 | NIST fabs 3 UHF arrays + 1 single pixel |  |  | 1.60 | [5 empty] | 30 |  |  |  | 2019-10-01 | 2019-11-13
|  |  | 2 | 1.77 | Assemble single pixels | Sbonder |  | 1.76 | 1.62 |  |  |  |  | 3 |  |  | 5 | 2019-11-14 | 2019-11-18
|  |  | 2 | 1.78 | test single pixels In DR4 |  |  | 1.77 | 1.42 |  |  |  |  | 17 |  |  | 6 | 2019-11-19 | 2019-12-12
|  |  | 2 | 1.79 | 3 UHF horns fab/shipped to Princeton |  |  | 1.61 | [5 empty] | 30 |  |  | 4 | 2019-09-24 | 2019-11-05
|  |  | 2 | 1.80 | Assemble 3 UFMs w/ C1-C3 | Sbonder |  | 1.22 | 1.76 | 1.77 | 1.79 |  |  | 6 |  |  | 5 | 2019-11-20 | 2019-11-27
|  |  | 2 | 1.81 | Test 3 UFMs in DR2 |  | 3 UHF-h | 1.63 |  | 1.80 |  |  |  | 30 |  |  | g | 2019-11-29 | 2020-01-14
|  |  | 2 | 1.82 | Test 1 of the above 3 UFM @ UCSD |  |  | 1.81 | 1.18 |  |  |  |  | 30 |  |  | r | 2020-01-15 | 2020-02-27
|  |  | 2 | 1.83 | NIST fab 6 sets of MMBs | [6 empty] | 2019-12-16 | 2020-01-15 | 10 |  |  |  | 2019-12-16 | 2020-01-15
|  |  | 3 | 1.83.1 | Fabrication 3 sets DC(I1-I3) |  |  | 1.64.7 | [5 empty] | 10 |  |  |  | 2019-12-16 | 2019-12-31
|  |  | 3 | 1.83.2 | Fabrication/screen/ship 2 sets resonators(I2-I3) |  |  | 1.64.4 | [5 empty] | 14 |  |  |  | 2020-07-16 | 2020-08-05
|  |  | 3 | 1.83.3 | Fabrication/screen/ship 2 sets resonators(I4-I5) |  |  | 1.83.2 | [5 empty] | 14 |  |  |  | 2020-08-06 | 2020-08-25
|  |  | 3 | 1.83.4 | Fabrication/screen/ship 2 sets resonators(I6-J1) |  |  | 1.83.3 | [5 empty] | 14 |  |  |  | 2020-08-26 | 2020-09-16
|  |  | 3 | 1.83.5 | Fabrication 3 sets RF/cap (I1-I3) |  |  | 1.64.6 | [5 empty] | 10 |  |  |  | 2019-12-16 | 2019-12-31
|  |  | 3 | 1.83.6 | Fabrication 3 sets RF/cap (I4-I6) |  |  | 1.83.5 | [5 empty] | 10 |  |  |  | 2020-01-02 | 2020-01-15
|  |  | 3 | 1.83.7 | Fabrication 3 sets DC(I4-I6) |  |  | 1.83.1 | [5 empty] | 10 |  |  |  | 2020-01-02 | 2020-01-15
|  |  | 2 | 1.84 | Screen DC wafers (I1-I6) in DR3 |  |  | 1.83.7 | 1.83.1 | 1.28 |  |  |  | 10 |  |  | o | 2020-01-24 | 2020-02-06
|  |  | 2 | 1.85 | Assemble 6 MMBs (I1-I6) | Lbonder |  | 1.66 | 1.84 | 1.83.6 | 1.83.2 |  |  | 34 |  |  | k | 2020-08-06 | 2020-09-24
|  |  | 2 | 1.86 | Test 3 MMBs (I1-I3) in DR1 |  | 48 MMBs | 1.85 | 1.68 |  |  |  |  | 15 |  |  | p | 2020-11-12 | 2020-12-03
|  |  | 2 | 1.87 | Test 3 MMBs (I4-I6) in DR1 |  | 51 MMBs | 1.85 | 1.86 |  |  |  |  | 15 |  |  | p | 2020-12-04 | 2020-12-24
|  |  | 2 | 1.88 | NIST fab 6 sets of MMBs | [6 empty] | 2020-01-16 | 2020-02-13 | 10 |  |  |  | 2020-01-16 | 2020-02-13
|  |  | 3 | 1.88.1 | Fabrication 3 sets DC(J1-J3) |  |  | 1.83.7 | [5 empty] | 10 |  |  |  | 2020-01-16 | 2020-01-30
|  |  | 3 | 1.88.2 | Fabrication/screen/ship 2 sets resonators(J2-J3) |  |  | 1.83.4 | [5 empty] | 14 |  |  |  | 2020-09-17 | 2020-10-06
|  |  | 3 | 1.88.3 | Fabrication/screen/ship 2 sets resonators(J4-J5) |  |  | 1.88.2 | [5 empty] | 14 |  |  |  | 2020-10-07 | 2020-10-27
|  |  | 3 | 1.88.4 | Fabrication/screen/ship 2 sets resonators(J6-K1) |  |  | 1.88.3 | [5 empty] | 14 |  |  |  | 2020-10-28 | 2020-11-17
|  |  | 3 | 1.88.5 | Fabrication 3 sets RF/cap (J1-J3) |  |  | 1.83.5 | [5 empty] | 10 |  |  |  | 2020-01-02 | 2020-01-15
|  |  | 3 | 1.88.6 | Fabrication 3 sets RF/cap (J4-J6) |  |  | 1.88.5 | [5 empty] | 10 |  |  |  | 2020-01-16 | 2020-01-30
|  |  | 3 | 1.88.7 | Fabrication 3 sets DC(J4-J6) |  |  | 1.88.1 | [5 empty] | 10 |  |  |  | 2020-01-31 | 2020-02-13
|  |  | 2 | 1.89 | Screen DC wafers (J1-J6) in DR3 |  |  | 1.88.7 | 1.88.1 | 1.84 |  |  |  | 10 |  |  | o | 2020-02-14 | 2020-02-28
|  |  | 2 | 1.90 | Assemble 6 MMBs (J1-J6) | Lbonder |  | 1.85 | 1.89 | 1.88.6 | 1.88.2 |  |  | 34 |  |  | k | 2020-10-07 | 2020-11-25
|  |  | 2 | 1.91 | Test 3 MMBs (J1-J3) in DR1 |  | 54 MMBs | 1.90 | 1.87 |  |  |  |  | 15 |  |  | p | 2020-12-28 | 2021-01-19
|  |  | 2 | 1.92 | Test 3 MMBs (J4-J6) in DR1 |  | 57 MMBs | 1.90 | 1.91 |  |  |  |  | 15 |  |  | p | 2021-01-20 | 2021-02-09
|  |  | 2 | 1.93 | NIST fabs 3 arrays |  |  | 1.76 | [5 empty] | 30 |  |  |  | 2019-11-14 | 2019-12-30
|  |  | 2 | 1.94 | 3 UHF horns fab/shipped to Princeton |  |  | 1.79 | [5 empty] | 30 |  |  | 4 | 2019-11-06 | 2019-12-19
|  |  | 2 | 1.95 | Assemble 3 UFMs w/C4-C6 | Sbonder |  | 1.93 | 1.80 | 1.94 | 1.23 |  |  | 6 |  |  | 5 | 2019-12-31 | 2020-01-08
|  |  | 2 | 1.96 | Test 3 UFMs in DR2 |  | 6 UHF-h | 1.95 | 1.81 |  |  |  |  | 30 |  |  | g | 2020-01-15 | 2020-02-27
|  |  | 2 | 1.97 | UCB fabs 6 arrays |  |  | 1.69 | [5 empty] | 50 |  |  | 2 | 2019-11-01 | 2020-01-16
|  |  | 2 | 1.98 | 3 sets of lenslet wafers fabricated |  |  | 1.73 | [5 empty] | 40 |  |  | 1 | 2020-02-03 | 2020-03-30
|  |  | 2 | 1.99 | Assemble 3 UCB UFMs w/ I1-I3 | Bbonder |  | 1.97 | 1.74 | 1.86 | 1.98 |  |  | 7 |  |  | 3 | 2020-12-04 | 2020-12-14
|  |  | 2 | 1.100 | Test 3 UFMs in DR3 | LATR4 | 15 MF-l | 1.99 | 1.33 |  |  |  |  | 30 |  |  | o | 2020-12-15 | 2021-01-28
|  |  | 2 | 1.101 | 3 sets of lenslet wafers fabricated |  |  | 1.98 | [5 empty] | 40 |  |  | 1 | 2020-03-31 | 2020-05-29
|  |  | 2 | 1.102 | Assemble 3 UCB UFMs w/ I4-I6 | Bbonder |  | 1.99 | 1.97 | 1.87 | 1.101 |  |  | 7 |  |  | 3 | 2020-12-28 | 2021-01-06
|  |  | 2 | 1.103 | Test 3 UFMs in DR3 | LATR5 | 18 MF-l | 1.102 | 1.100 |  |  |  |  | 30 |  |  | o | 2021-01-29 | 2021-03-12
|  |  | 2 | 1.104 | NIST fab 6 sets of MMBs | [6 empty] | 2020-02-14 | 2020-03-13 | 10 |  |  |  | 2020-02-14 | 2020-03-13
|  |  | 3 | 1.104.1 | Fabrication 3 sets DC(K1-K3) |  |  | 1.88.7 | [5 empty] | 10 |  |  |  | 2020-02-14 | 2020-02-28
|  |  | 3 | 1.104.2 | Fabrication/screen/ship 2 sets resonators(K2-K3) |  |  | 1.88.2 | [5 empty] | 14 |  |  |  | 2020-10-07 | 2020-10-27
|  |  | 3 | 1.104.3 | Fabrication/screen/ship 2 sets resonators(K4-K5) |  |  | 1.104.2 | [5 empty] | 14 |  |  |  | 2020-10-28 | 2020-11-17
|  |  | 3 | 1.104.4 | Fabrication/screen/ship 2 sets resonators(K6-K1) |  |  | 1.104.3 | [5 empty] | 14 |  |  |  | 2020-11-18 | 2020-12-08
|  |  | 3 | 1.104.5 | Fabrication 3 sets RF/cap (K1-K3) |  |  | 1.88.6 | [5 empty] | 10 |  |  |  | 2020-01-31 | 2020-02-13
|  |  | 3 | 1.104.6 | Fabrication 3 sets RF/cap (K4-K6) |  |  | 1.104.5 | [5 empty] | 10 |  |  |  | 2020-02-14 | 2020-02-28
|  |  | 3 | 1.104.7 | Fabrication 3 sets DC(K4-K6) |  |  | 1.104.1 | [5 empty] | 10 |  |  |  | 2020-03-02 | 2020-03-13
|  |  | 2 | 1.105 | Screen DC wafers (K1-K6) in DR3 |  |  | 1.104.7 | 1.104.1 | 1.116 |  |  |  | 10 |  |  | o | 2020-04-06 | 2020-04-21
|  |  | 2 | 1.106 | Assemble 6 MMBs (K1-K6) | Lbonder |  | 1.90 | 1.105 | 1.104.6 | 1.104.2 |  |  | 34 |  |  | k | 2020-11-27 | 2021-01-15
|  |  | 2 | 1.107 | Test 3 MMBs (K1-K3) in DR1 |  | 60 MMBs | 1.106 | 1.92 |  |  |  |  | 15 |  |  | p | 2021-02-10 | 2021-03-03
|  |  | 2 | 1.108 | Test 3 MMBs (K4-K6) in DR3 |  | 63 MMBs | 1.106 | 1.122 |  |  |  |  | 15 |  |  | o | 2021-04-28 | 2021-05-19
|  |  | 2 | 1.109 | NIST fab 6 sets of MMBs | [6 empty] | 2020-03-16 | 2020-04-14 | 10 |  |  |  | 2020-03-16 | 2020-04-14
|  |  | 3 | 1.109.1 | Fabrication 3 sets DC(L1-L3) |  |  | 1.104.7 | [5 empty] | 10 |  |  |  | 2020-03-16 | 2020-03-27
|  |  | 3 | 1.109.2 | Fabrication/screen/ship 2 sets resonators(L2-L3) |  |  | 1.104.4 | [5 empty] | 14 |  |  |  | 2020-12-09 | 2020-12-29
|  |  | 3 | 1.109.3 | Fabrication/screen/ship 2 sets resonators(L4-L5) |  |  | 1.109.2 | [5 empty] | 14 |  |  |  | 2020-12-30 | 2021-01-20
|  |  | 3 | 1.109.4 | Fabrication/screen/ship 2 sets resonators(L6-M1) |  |  | 1.109.3 | [5 empty] | 14 |  |  |  | 2021-01-21 | 2021-02-09
|  |  | 3 | 1.109.5 | Fabrication 3 sets RF/cap (L1-L3) |  |  | 1.104.6 | [5 empty] | 10 |  |  |  | 2020-03-02 | 2020-03-13
|  |  | 3 | 1.109.6 | Fabrication 3 sets RF/cap (L4-L6) |  |  | 1.109.5 | [5 empty] | 10 |  |  |  | 2020-03-16 | 2020-03-27
|  |  | 3 | 1.109.7 | Fabrication 3 sets DC(L4-L6) |  |  | 1.109.1 | [5 empty] | 10 |  |  |  | 2020-03-30 | 2020-04-14
|  |  | 2 | 1.110 | Screen DC wafers (L1-L6) in DR3 |  |  | 1.109.7 | 1.109.1 | 1.105 |  |  |  | 10 |  |  | o | 2020-04-22 | 2020-05-06
|  |  | 2 | 1.111 | Assemble 6 MMBs (L1-L6) | Lbonder |  | 1.106 | 1.110 | 1.109.6 | 1.106 |  |  | 34 |  |  | k | 2021-01-19 | 2021-03-08
|  |  | 2 | 1.112 | Test 3 MMBs (L1-L3) in DR3 |  | 66 MMBs | 1.111 | 1.108 |  |  |  |  | 15 |  |  | o | 2021-05-20 | 2021-06-10
|  |  | 2 | 1.113 | NIST fabs 3 arrays |  |  | 1.93 | [5 empty] | 30 |  |  |  | 2019-12-31 | 2020-02-12
|  |  | 2 | 1.114 | 3 UHF horns fab/shipped to Princeton |  |  | 1.94 | [5 empty] | 30 |  |  | 4 | 2019-12-20 | 2020-02-05
|  |  | 2 | 1.115 | Assemble 3 UFMs w/D1-D3 | Sbonder |  | 1.113 | 1.27 | 1.95 | 1.114 |  |  | 6 |  |  | k | 2020-02-13 | 2020-02-21
|  |  | 2 | 1.116 | Test 3 UFMs in DR3 | SAT2 | 9 UHF-h | 1.115 | 1.28 |  |  |  |  | 30 |  |  | o | 2020-02-24 | 2020-04-03
|  |  | 2 | 1.117 | UCB fabs 6 LF arrays & single pixels |  |  | 1.97 | [5 empty] | 50 |  |  | 2 | 2020-01-17 | 2020-03-30
|  |  | 2 | 1.118 | Assemble single pixels | Sbonder |  | 1.117 | 1.115 |  |  |  |  | 3 |  |  | 5 | 2020-03-31 | 2020-04-02
|  |  | 2 | 1.119 | test single pixels UCSD |  |  | 1.118 | 1.82 |  |  |  |  | 17 |  |  | r | 2020-04-03 | 2020-04-29
|  |  | 2 | 1.120 | 3 sets of lenslet wafers fabricated |  |  | 1.101 | [5 empty] | 40 |  |  | 1 | 2020-06-01 | 2020-07-24
|  |  | 2 | 1.121 | Assemble 3 UCB UFMs w/ J1-J3 | Bbonder |  | 1.117 | 1.91 | 1.102 | 1.120 |  |  | 7 |  |  | 3 | 2021-01-20 | 2021-01-28
|  |  | 2 | 1.122 | Test 3 UFMs in DR3 |  | 3 LF-l | 1.121 | 1.103 |  |  |  |  | 30 |  |  | o | 2021-03-15 | 2021-04-27
|  |  | 2 | 1.123 | 3 sets of lenslet wafers fabricated |  |  | 1.120 | [5 empty] | 40 |  |  | 1 | 2020-07-27 | 2020-09-23
|  |  | 2 | 1.124 | Assemble 3 UCB UFMs w/ J4-J6 | Bbonder |  | 1.121 | 1.117 | 1.92 | 1.123 |  |  | 7 |  |  | 3 | 2021-02-10 | 2021-02-19
|  |  | 2 | 1.125 | Test 3 UFMs in DR2 | LATR7 | 6 LF-l | 1.124 | 1.129 |  |  |  |  | 30 |  |  | g | 2021-02-22 | 2021-04-06
|  |  | 2 | 1.126 | NIST fabs 3 arrays |  |  | 1.153 | [5 empty] | 30 |  |  |  | 2020-08-07 | 2020-09-21
|  |  | 2 | 1.127 | 3 UHF horns fab/shipped to Princeton |  |  | 1.154 | [5 empty] | 30 |  |  | 4 | 2020-06-18 | 2020-07-29
|  |  | 2 | 1.128 | Assemble 3 UFMs w/F1-F3 | Sbonder |  | 1.126 | 1.53 | 1.118 | 1.127 |  |  | 6 |  |  | 5 | 2020-09-22 | 2020-09-29
|  |  | 2 | 1.129 | Test 3 UFMs in DR3 | LATR3 | 12 UHF-h | 1.128 | 1.81 |  |  |  |  | 30 |  |  | o | 2020-09-30 | 2020-11-12
|  |  | 2 | 1.130 | UCB fabs 6 arrays |  |  | 1.117 | [5 empty] | 50 |  |  | 2 | 2020-03-31 | 2020-06-12
|  |  | 2 | 1.131 | 3 sets of lenslet wafers fabricated |  |  | 1.123 | [5 empty] | 40 |  |  | 1 | 2020-09-24 | 2020-11-20
|  |  | 2 | 1.132 | Assemble 3 UCB UFMs w/ K1-K3 | Bbonder |  | 1.130 | 1.124 | 1.107 | 1.131 |  |  | 7 |  |  | 3 | 2021-03-04 | 2021-03-12
|  |  | 2 | 1.133 | Test 3 UFMs in DR3 |  | 9 LF-l | 1.132 | 1.112 |  |  |  |  | 30 |  |  | o | 2021-06-11 | 2021-07-22
|  |  | 2 | 1.134 | 3 sets of lenslet wafers fabricated |  |  | 1.131 | [5 empty] | 40 |  |  | 1 | 2020-11-23 | 2021-01-21
|  |  | 2 | 1.135 | Assemble 3 UCB UFMs w/ K4-K6 | Bbonder |  | 1.132 | 1.132 | 1.108 | 1.134 |  |  | 7 |  |  | 3 | 2021-05-20 | 2021-05-28
|  |  | 2 | 1.136 | Test 3 UFMs in DR1 |  | 12 LF-l | 1.135 | 1.107 |  |  |  |  | 30 |  |  | p | 2021-06-01 | 2021-07-12
|  |  | 2 | 1.137 | NIST fabs 3 arrays |  |  | 1.126 | [5 empty] | 30 |  |  |  | 2020-09-22 | 2020-11-03
|  |  | 2 | 1.138 | 3 UHF horns fab/shipped to Princeton |  |  | 1.127 | [5 empty] | 30 |  |  | 4 | 2020-07-30 | 2020-09-14
|  |  | 2 | 1.139 | Assemble 3 UFMs w/ F4-F6 | Lbonder |  | 1.137 | 1.54 | 1.52 | 1.138 |  |  | 6 |  |  | k | 2020-11-04 | 2020-11-12
|  |  | 2 | 1.140 | Test 3 UFMs in DR2 | LATR6 | 15 UHF-h | 1.139 | 1.63 |  |  |  |  | 30 |  |  | g | 2020-11-13 | 2020-12-28
|  |  | 2 | 1.141 | UCB fabs 3 arrays |  |  | 1.130 | [5 empty] | 25 |  |  | 2 | 2020-06-15 | 2020-07-17
|  |  | 2 | 1.142 | 3 sets of lenslet wafers fabricated |  |  | 1.134 | [5 empty] | 40 |  |  | 1 | 2021-01-22 | 2021-03-19
|  |  | 2 | 1.143 | Assemble 3 UCB UFMs w/ L1-L3 | Bbonder |  | 1.141 | 1.112 | 1.135 | 1.142 |  |  | 3.5 |  |  | 3 | 2021-06-11 | 2021-06-15
|  |  | 2 | 1.144 | Test 3 UFMs in DR3 |  |  | 1.143 | 1.133 |  |  |  |  | 30 |  |  | o | 2021-07-23 | 2021-09-07
|  |  | 2 | 1.145 | NIST fabs 3 arrays |  |  | 1.113 | [5 empty] | 40 |  |  |  | 2020-02-13 | 2020-04-09
|  |  | 2 | 1.146 | 3 MF horns fab/shipped to Princeton |  |  | 1.114 | [5 empty] | 30 |  |  | 4 | 2020-02-06 | 2020-03-19
|  |  | 2 | 1.147 | Assemble 3 UFMs w/D4-D6 | Lbonder |  | 1.145 | 1.28 | 1.52 | 1.146 |  |  | 10 |  |  | k | 2020-04-23 | 2020-05-07
|  |  | 2 | 1.148 | Test 3 UFMs in DR2 |  | 12 MF-h | 1.147 | 1.96 |  |  |  |  | 25 |  |  | g | 2020-05-08 | 2020-06-12
|  |  | 2 | 1.149 | NIST fabs 3 arrays |  |  | 1.145 | [5 empty] | 40 |  |  |  | 2020-04-14 | 2020-06-10
|  |  | 2 | 1.150 | 3 MF horns fab/shipped to Princeton |  |  | 1.146 | [5 empty] | 30 |  |  | 4 | 2020-03-20 | 2020-05-05
|  |  | 2 | 1.151 | Assemble 3 UFMs w/ E1-E3 | Lbonder |  | 1.149 | 1.32 | 1.147 | 1.150 |  |  | 10 |  |  | k | 2020-06-11 | 2020-06-24
|  |  | 2 | 1.152 | Test 3 UFMs in DR2 |  | 15 MF-h | 1.151 | 1.148 |  |  |  |  | 25 |  |  | g | 2020-06-25 | 2020-07-29
|  |  | 2 | 1.153 | NIST fabs 3 arrays |  |  | 1.149 | [5 empty] | 40 |  |  |  | 2020-06-11 | 2020-08-06
|  |  | 2 | 1.154 | 3 MF horns fab/shipped to Princeton |  |  | 1.150 | [5 empty] | 30 |  |  | 4 | 2020-05-06 | 2020-06-17
|  |  | 2 | 1.155 | Assemble 3 UFMs w/ E4-E6 | Lbonder |  | 1.153 | 1.151 | 1.33 | 1.154 |  |  | 10 |  |  | k | 2020-08-07 | 2020-08-20
|  |  | 2 | 1.156 | Test 3 UFMs in DR1 | SAT3 | 18 MF-h | 1.155 | 1.148 |  |  |  |  | 25 |  |  | p | 2020-08-21 | 2020-09-28
Formulas:
Monthly = IF(N12<>"",N12,IF([Display:]=" - "," - ",IF(O12<>"",WORKDAY.INTL([Display:],O12-1,weekend,holidays),[Display:]+MAX(P12,1)-1)))
Show Weekends (Daily view only)
Note on E6: Project Start Date Enter the Start Date for the Project. Avoid choosing a date that falls on a Saturday or Sunday.
Note on S6: Daily / Weekly / Monthly: Use this to change the gantt chart view to Weekly or Monthly if you want to see a larger range of dates. Note that the monthly view results in a loss of detail.
Note on S7: Display Week / Display Month: Use this to change the starting week or month shown in the gantt chart.
Note on E8: Today's Date: Use the formula =TODAY() to make the red line in the gantt chart display the current day, or enter the date manually.
Note on D9: WBS Level: Choose the WBS (Work Breakdown Structure) level from the drop-down in this column.
Note on E9: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to automatically update the numbering.
Note on F9: Task Description Enter the name of each task and sub-task. The task description is automatically indented using conditional formatting based on the WBS Level column.
Note on G9: Task Lead Enter the name of the Task Lead in this column.
Note on I9: Predecessor Tasks: You may use this column to calculate the start date for the task based on the end date of the Predecessor you reference. Use a formula like =A13 to reference the WBS of the Predecessor task that must be completed before this task can start. You can also enter the WBS as a text value by entering an apostrophe before the number like '2.3. Avoid circular references, such as choosing the current task as its own Predecessor. Using this column assumes that you want the task to start on the next work day. See the Help worksheet for more examples of using formulas to create task dependencies.
Note on M9: Start Date You can manually enter the Start date for each task, use the Predecessor column to have a Start date calculated automatically, or use a formula to create a dependency on some other cell. See the Help worksheet for examples of creating dependencies.
Note on N9: End Date If you want to define the End date instead of calculating what it should be, enter the date in this column. Otherwise, enter a value in the Work Days or Calendar Days column to define the duration of the task.
Note on O9: Work Days Enter the number of Work Days that you estimate this task will require to complete. Work Days exclude the weekend (defined in the Help worksheet) and the holidays listed in the Holidays worksheet.
Note on P9: Duration: Calendar Days If you want to enter the number of calendar days instead of the number of work days, enter a value in this column.
Note on Q9: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on R9: Color (Optional): Enter a color code in this column to change the color of the incomplete portion of the gantt chart. 1 - 6 = theme-based accent colors k = black r = red o = orange y = yellow p = purple g = green
Note on S9: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1,holidays) to set the Start date to the next work day (excluding weekends and holidays), where enddate is the cell reference for the End date of the Predecessor task.
Note on T9: End Date The WORKDAY() function is used to calculate the ending date so that the End Date does not fall on a weekend or a holiday. If you choose to use the Duration as the input, the End date is calculated as the Start date + Duration - 1.
Note on U9: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on V9: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on W9: Calendar Days Complete [ You can hide this column prior to printing ] This column is calculated by multiplying the Work Days by the %Complete and using the WORKDAY() function to determine how many calendar days have been completed. Note: The conditional formatting used to create the gantt chart references this column.
Note on X9: Calendar Days Remaining [ You can hide this column prior to printing ] This column is calculated by subtracting the Days Complete from the Duration.
Note on Y9: Planned Start & End After creating the project schedule, you can copy the Start and End columns and use Paste Special > Values to paste the dates into the Planned Start and Planned End columns. The planned periods will be represented in the gantt chart using cross-hatching.

## R&D-Gantt
|  |  | Gantt Chart Template | [10 empty] | © 2006-2017 Vertex42.com |  |  | [Hide this row]
WBS 1.5 Gantt Chart for Progress to Detector & Readout Production Readiness Reviews, Simons Observatory
|  |  | Project Lead: Suzanne Staggs |  | Editor: Patty Ho
|  |  | Start: | 2018-10-19 | [13 empty] | Display: | Monthly
|  |  | End: | 2020-12-14 | [13 empty] | Month: | 1
|  |  | Today: | 2019-03-25 | [18 empty] | [42] | time axis 2018-10-01 to 2023-01-25
|  |  | Last edits | 2019-03-25 | [18 empty] | [42] | time axis 2018-10-01 to 2023-01-25
|  | WBS Level | WBS | Task | Note | Total Counts | Predecessors |  |  |  |  | Actual Start | Actual End | Work Days | Cal Days | % Done | Color | Actual Start | Actual End | Work Days | Cal Days | Days Done | Days Left | Planned Start | Planned End | 2018-10-01: 2018-10-01; 2018-11-01: 2018-11-01; 2018-12-01: 2018-12-01; 2019-01-01: 2019-01-01; 2019-02-01: 2019-02-01; 2019-03-01: 2019-03-01; 2019-04-01: 2019-04-01; 2019-05-01: 2019-05-01; 2019-06-01: 2019-06-01; 2019-07-01: 2019-07-01; 2019-08-01: 2019-08-01; 2019-09-01: 2019-09-01; 2019-10-01: 2019-10-01; 2019-11-01: 2019-11-01; 2019-12-01: 2019-12-01; 2020-01-01: 2020-01-01; 2020-02-01: 2020-02-01; 2020-03-01: 2020-03-01; 2020-04-01: 2020-04-01; 2020-05-01: 2020-05-01; 2020-06-01: 2020-06-01; 2020-07-01: 2020-07-01; 2020-08-01: 2020-08-01; 2020-09-01: 2020-09-01; 2020-10-01: 2020-10-01; 2020-11-01: 2020-11-01; 2020-12-01: 2020-12-01; 2021-01-01: 2021-01-01; 2021-02-01: 2021-02-01; 2021-03-01: 2021-03-01; 2021-04-01: 2021-04-01; 2021-05-01: 2021-05-01; 2021-06-01: 2021-06-01; 2021-07-01: 2021-07-01; 2021-08-01: 2021-08-01; 2021-09-01: 2021-09-01; 2021-10-01: 2021-10-01; 2021-11-01: 2021-11-01; 2021-12-01: 2021-12-01; 2022-01-01: 2022-01-01; 2022-02-01: 2022-02-01; 2022-03-01: 2022-03-01; 2022-04-01: 2022-04-01; 2022-05-01: 2022-05-01; 2022-06-01: 2022-06-01; 2022-07-01: 2022-07-01; 2022-08-01: 2022-08-01; 2022-09-01: 2022-09-01; 2022-10-01: 2022-10-01; 2022-11-01: 2022-11-01; 2022-12-01: 2022-12-01; 2023-01-01: 2023-01-01
[26 empty] | 2018-10-01 | [6 empty] | 2018-11-01 | [6 empty] | 2018-12-01 | [6 empty] | 2019-01-01 | [6 empty] | 2019-02-01 | [6 empty] | 2019-03-01 | [6 empty] | 2019-04-01 | [6 empty] | 2019-05-01 | [6 empty] | 2019-06-01 | [6 empty] | 2019-07-01 | [6 empty] | 2019-08-01 | [6 empty] | 2019-09-01 | [6 empty] | 2019-10-01 | [6 empty] | 2019-11-01 | [6 empty] | 2019-12-01 | [6 empty] | 2020-01-01 | [6 empty] | 2020-02-01 | [6 empty] | 2020-03-01 | [6 empty] | 2020-04-01 | [6 empty] | 2020-05-01 | [6 empty] | 2020-06-01 | [6 empty] | 2020-07-01 | [6 empty] | 2020-08-01 | [6 empty] | 2020-09-01 | [6 empty] | 2020-10-01 | [6 empty] | 2020-11-01 | [6 empty] | 2020-12-01 | [6 empty] | 2021-01-01 | [6 empty] | 2021-02-01 | [6 empty] | 2021-03-01 | [6 empty] | 2021-04-01 | [6 empty] | 2021-05-01 | [6 empty] | 2021-06-01 | [6 empty] | 2021-07-01 | [6 empty] | 2021-08-01 | [6 empty] | 2021-09-01 | [6 empty] | 2021-10-01 | [6 empty] | 2021-11-01 | [6 empty] | 2021-12-01 | [6 empty] | 2022-01-01 | [6 empty] | 2022-02-01 | [6 empty] | 2022-03-01 | [6 empty] | 2022-04-01 | [6 empty] | 2022-05-01 | [6 empty] | 2022-06-01 | [6 empty] | 2022-07-01 | [6 empty] | 2022-08-01 | [6 empty] | 2022-09-01 | [6 empty] | 2022-10-01 | [6 empty] | 2022-11-01 | [6 empty] | 2022-12-01 | [6 empty] | 2023-01-01
Parameter | Value | [24 empty] | 2018-10-01: 1; 2018-11-01: 2; 2018-12-01: 3; 2019-01-01: 4; 2019-02-01: 5; 2019-03-01: 6; 2019-04-01: 7; 2019-05-01: 8; 2019-06-01: 9; 2019-07-01: 10; 2019-08-01: 11; 2019-09-01: 12; 2019-10-01: 13; 2019-11-01: 14; 2019-12-01: 15; 2020-01-01: 16; 2020-02-01: 17; 2020-03-01: 18; 2020-04-01: 19; 2020-05-01: 20; 2020-06-01: 21; 2020-07-01: 22; 2020-08-01: 23; 2020-09-01: 24; 2020-10-01: 25; 2020-11-01: 26; 2020-12-01: 27; 2021-01-01: 28; 2021-02-01: 29; 2021-03-01: 30; 2021-04-01: 31; 2021-05-01: 32; 2021-06-01: 33; 2021-07-01: 34; 2021-08-01: 35; 2021-09-01: 36; 2021-10-01: 37; 2021-11-01: 38; 2021-12-01: 39; 2022-01-01: 40; 2022-02-01: 41; 2022-03-01: 42; 2022-04-01: 43; 2022-05-01: 44; 2022-06-01: 45; 2022-07-01: 46; 2022-08-01: 47; 2022-09-01: 48; 2022-10-01: 49; 2022-11-01: 50; 2022-12-01: 51; 2023-01-01: 52
Days to assembly MMB | 5 | 1 | 1 | Readout task | [ name ] | [12 empty] | - | - | - | - | - | -
Days to test in Pton small tail | 4 | 2 | 1.1 | MMB "mech design" finalized | [8 empty] | 2018-08-14 |  |  |  |  | 2018-08-14 | 2018-08-14 | 1 | 1 | 0 | 1
Days to test in Pton big tail | 7 | 2 | 1.2 | develop sloped etch for DC board | [13 empty] | #REF! | #REF!
|  | 2 | 1.3 | READOUT (RO) DR2 (part 1) | [8 empty] | 2018-08-14 |  |  |  |  | 2018-08-14 | 2018-08-14
|  | 2 | 1.4 | READOUT (RO) DR2 (part 2) | [8 empty] | 2018-09-11 |  |  |  |  | 2018-09-11 | 2018-09-11
|  | 2 | 1.5 | fab 2 MMBs with fake (thru) resonators |  |  | 1.1 | [5 empty] | 2018-10-17 |  |  |  |  | 2018-10-17 | 2018-10-17
|  | 2 | 1.6 | NIST screening demonstrated | [13 empty] | - | -
|  | 2 | 1.7 | fab RF wafer for flex coax use in MMB-v0' | [13 empty] | - | -
|  | 2 | 1.8 | draw final DC wafers | [13 empty] | - | -
|  | 2 | 1.9 | draw final RF wafers | [13 empty] | - | -
|  | 2 | 1.10 | fab umux for 4 MMBs | [8 empty] | 2018-12-21 | 40 |  |  |  | 2018-10-26 | 2018-12-21
|  | 2 | 1.11 | resonators screened at NIST; all MMB parts g2g |  |  | 1.6 | 1.8 | 1.9 | draw final RF wafers | 0 | [6 empty] | #VALUE! | #VALUE!
|  | 2 | 1.12 | SMuRF board upgrades (2018a-->2018b) |  |  | 1.3 | 1.4 | [9 empty] | 2018-09-12 | 2018-09-12
|  | 2 | 1.13 | RF/EMI stress test/ demo |  |  | 1.16 | [10 empty] | 2019-02-19 | 2019-02-19
|  | 2 | 1.14 | SMuRF s/w suite complete |  |  | 1.16 | [10 empty] | 2019-02-19 | 2019-02-19
|  | 2 | 1.15 | finalize wiring harnesses LATR/SAT |  |  | 1.16 | [10 empty] | 2019-02-19 | 2019-02-19
|  | 2 | 1.16 | Readout PRR | [8 empty] | 2019-02-18 |  |  |  |  | 2019-02-18 | 2019-02-18
|  | 1 | 2 | Detector task | [13 empty] | - | -
|  | 2 | 2.1 | MF detector "mech design finished" | [8 empty] | 2018-08-14 |  |  |  |  | 2018-08-14 | 2018-08-14
|  | 2 | 2.2 | MF bandpass reqs finalized | [8 empty] | 2018-08-21 |  |  |  |  | 2018-08-21 | 2018-08-21
|  | 2 | 2.3 | NIST MF array layout |  |  | 2.2 | 2.1 | [9 empty] | 2018-08-22 | 2018-08-22
|  | 2 | 2.4 | UHF SP verification | [13 empty] | - | -
|  | 2 | 2.5 | UHF design decisions (lumped absorber, PdAu grid, bands) | [13 empty] | - | -
|  | 2 | 2.6 | FInalize UHF choke design (so wafers can be ordered) | [8 empty] | 2018-09-04 |  |  |  |  | 2018-09-04 | 2018-09-04
|  | 2 | 2.7 | UCB MF array layout |  |  | 2.2 | 2.1 |  |  |  |  | 2018-08-28 |  |  |  |  | 2018-08-22 | 2018-08-28
|  | 2 | 2.8 | DETECTOR DR2/ NIST | [8 empty] | 2018-08-21 |  |  |  |  | 2018-08-21 | 2018-08-21
|  | 2 | 2.9 | DETECTOR DR2 / UCB | [8 empty] | 2018-08-28 |  |  |  |  | 2018-08-28 | 2018-08-28
|  | 2 | 2.10 | UHF array layout |  |  | 2.4 | 2.5 | [9 empty] | #VALUE! | #VALUE!
|  | 2 | 2.11 | LF params (bandpass) finalized | [13 empty] | - | -
|  | 2 | 2.12 | LF "mech design" finished | [13 empty] | - | -
|  | 2 | 2.13 | MF+UHF proto horn array fabricated | [8 empty] | 2018-12-10 |  |  |  |  | 2018-12-10 | 2018-12-10
|  | 2 | 2.14 | MF+UHF proto horn array tested | [9 empty] | 7 |  |  |  | - | -
|  | 2 | 2.15 | UHF single pixel array made with UHF proto array ready for bandpass & efficiency tests at NIST | [13 empty] | - | -
|  | 2 | 2.16 | NIST UHF proto array delivered | [13 empty] | - | -
|  | 2 | 2.17 | NIST MF proto array delivered | [13 empty] | - | -
|  | 2 | 2.18 | UCB MF SP#2 design | [8 empty] | 2018-07-03 |  |  |  |  | 2018-07-03 | 2018-07-03
|  | 2 | 2.19 | UCB MF SP#2 fab | [8 empty] | 2018-07-31 |  |  |  |  | 2018-07-31 | 2018-07-31
|  | 2 | 2.20 | UCB MF SP#2 verification | [8 empty] | 2018-08-14 |  |  |  |  | 2018-08-14 | 2018-08-14
|  | 2 | 2.21 | UCB MF monolithic 7-or-19 element lenslets with epoxy first test | [8 empty] | 2018-08-27 | 30 |  |  |  | 2018-07-16 | 2018-08-27
|  | 2 | 2.22 | UCB MF array & SP#3 layout | [8 empty] | 2018-09-10 |  |  |  |  | 2018-09-10 | 2018-09-10
|  | 2 | 2.23 | Install 170 mK AlMn target | [8 empty] | 2018-07-31 |  |  |  |  | 2018-07-31 | 2018-07-31
|  | 2 | 2.24 | Begin hand-assembled 19-element epoxy lenslets (if needed) | [13 empty] | - | -
|  | 2 | 2.25 | UCB MF array#3 and SP#3 delivered/fabbed | [8 empty] | 2018-10-08 |  |  |  |  | 2018-10-08 | 2018-10-08
|  | 2 | 2.26 | Full-size MF monolithic lenslet array with epoxy tested | [8 empty] | 2018-10-15 |  |  |  |  | 2018-10-15 | 2018-10-15
|  | 2 | 2.27 | UCB MF SP#3 verfication |  |  | 2.25 | 2.22 |  |  |  |  | 2018-10-23 |  |  |  |  | 2018-10-09 | 2018-10-23
|  | 2 | 2.28 | UCB LF+MF SP#4 and LF? array #4 layout |  |  | 2.27 | 2.12 | 2.11 | LF params (bandpass) finalized | 0 |  | 2018-11-19 |  |  |  |  | #VALUE! | 2018-11-19
|  | 2 | 2.29 | NIST releases stepper PO | [8 empty] | 2018-09-28 |  |  |  |  | 2018-09-28 | 2018-09-28
|  | 2 | 2.30 | NIST stepper preliminary status | [8 empty] | 2018-12-18 |  |  |  |  | 2018-12-18 | 2018-12-18
|  | 2 | 2.31 | NIST DETECTOR PRR | [7 empty] | 2019-04-05 | [5 empty] | 2019-04-05 | 2019-04-05
|  | 2 | 2.32 | NIST stepper up & going | [13 empty] | - | -
|  | 2 | 2.33 | UCB LF+MF SP#4 and LF? array #4 fab |  |  | 2.28 | [10 empty] | 2018-11-20 | 2018-11-20
|  | 2 | 2.34 | UCB LF+MF SP#4 verification |  |  | 2.33 | [10 empty] | 2018-11-21 | 2018-11-21
|  | 2 | 2.35 | UFM TESTING STARTS | [13 empty] | - | -
|  | 2 | 2.36 | DETECTOR PRODUCTION THROUGH 2019 | [13 empty] | - | -
|  | 1 | 3 | Integration task | [13 empty] | - | -
|  | 2 | 3.1 | UFM PDR | [13 empty] | - | - | - | - | - | -
|  | 2 | 3.2 | MMB-V0 assembled & ready for test @UCSD | [8 empty] | 2018-10-18 |  |  | 100% | k | 2018-10-18 | 2018-10-18 | 1 | 1 | 1 | 0
|  | 2 | 3.3 | MMB-V0 first test results in | [8 empty] | 2018-10-30 |  |  | 100% | r | 2018-10-30 | 2018-10-30 | 1 | 1 | 1 | 0
|  | 2 | 3.4 | Single MUX chip @ Pton | [8 empty] | 2018-11-13 |  |  | 100% | o | 2018-11-13 | 2018-11-13 | 1 | 1 | 1 | 0
|  | 2 | 3.5 | MMB-V0b assembled & ready for test @ UCSD | [8 empty] | 2018-11-19 |  |  | 100% | k | 2018-11-19 | 2018-11-19 | 1 | 1 | 1 | 0
|  | 2 | 3.6 | MMB-V0b returned b/c Duroid fell off during shipping | [8 empty] | 2018-11-27 |  |  | 100% | r | 2018-11-27 | 2018-11-27 | 1 | 1 | 1 | 0
|  | 2 | 3.7 | Single MUX chip @ Pton |  |  | 3.4 | [5 empty] | 2018-11-20 |  |  | 100% | o | 2018-11-14 | 2018-11-20 | 5 | 7 | 7 | 0
|  | 2 | 3.8 | Single MUX chip test results in |  |  | 3.7 | [5 empty] | 2018-12-04 |  |  | 100% | o | 2018-11-21 | 2018-12-04 | 9 | 14 | 14 | 0
|  | 2 | 3.9 | Reassemble MMB-v0 -- call it MMB-V0a -- and ready for test @ Pton | [8 empty] | 2018-12-06 |  |  | 100% | k | 2018-12-06 | 2018-12-06 | 1 | 1 | 1 | 0
|  | 2 | 3.10 | MMB-V0a first test results in |  |  | 3.9 | 3.8 |  |  |  |  | 2018-12-11 |  |  | 100% | o | 2018-12-07 | 2018-12-11 | 3 | 5 | 5 | 0
|  | 2 | 3.11 | MMB-V0a ready for test @ UCSD |  |  | 3.10 |  |  |  |  | 2018-12-14 | 2018-12-17 |  |  | 100% | k | 2018-12-14 | 2018-12-17 | 2 | 4 | 4 | 0
|  | 2 | 3.12 | MMB-V0a remeasured S21 + crosstalk results in |  |  | 3.11 | [6 empty] | 5 |  | 100% | r | 2018-12-18 | 2018-12-24 | 5 | 7 | 7 | 0
|  | 2 | 3.13 | MMB-V0a test results in (TDR) |  |  | 3.12 | [6 empty] | 7 |  | 100% | r | 2018-12-27 | 2019-01-07 | 7 | 12 | 12 | 0
|  | 2 | 3.14 | MMB-V0a ready for test @ Cornell |  |  | 3.13 | [6 empty] | 3 |  | 100% | k | 2019-01-08 | 2019-01-10 | 3 | 3 | 3 | 0
|  | 2 | 3.15 | MMB-V0a Cornell S21 test results in |  |  | 3.14 | [6 empty] | 10 |  | 100% | g | 2019-01-11 | 2019-01-25 | 10 | 15 | 15 | 0
|  | 2 | 3.16 | MMB-V0b reassembled & ready for test @ Pton | [7 empty] | 2018-12-12 |  | 7 |  | 100% | k | 2018-12-12 | 2018-12-20 | 7 | 9 | 9 | 0
|  | 2 | 3.17 | MMB-V0b reassembled first test results in |  |  | 3.16 | 3.10 |  |  |  |  | 2018-12-26 |  |  | 100% | o | 2018-12-21 | 2018-12-26 | 2 | 6 | 6 | 0
|  | 2 | 3.18 | Coax line testing @Mich | [7 empty] | 2018-12-26 | 2018-12-29 |  |  | 100% | p | 2018-12-26 | 2018-12-29 | 2 | 4 | 2 | 2
|  | 2 | 3.19 | 1-flex-coax tested cold thru RF chain for S21 @ Mich |  |  | 3.18 |  |  |  |  | 2019-01-05 | 2019-01-09 | 2 |  | 100% | p | 2019-01-05 | 2019-01-09 | 2 | 5 | 3 | 2
|  | 2 | 3.20 | MMB- V0b' (= MMB-V0b reassembled w/o interface chip) ready @ Pton |  |  | 3.17 | [5 empty] | 2018-12-28 | 2 |  | 100% | k | 2018-12-27 | 2018-12-28 | 2 | 2 | 2 | 0
|  | 2 | 3.21 | MMB-V0b' results in |  |  | 3.20 | [6 empty] | 5 |  | 100% | o | 2018-12-31 | 2019-01-07 | 5 | 8 | 8 | 0
|  | 2 | 3.22 | MMB- V0c (= MMB-V0b' reassembled w RF cap/wall) ready @ Pton |  |  | 3.21 | [5 empty] | 2019-01-10 | 4 |  | 100% | k | 2019-01-08 | 2019-01-10 | 4 | 3 | 3 | 0
|  | 2 | 3.23 | MMB-V0c results in and warm-up |  |  | 3.22 | [6 empty] | 7 |  | 100% | o | 2019-01-11 | 2019-01-22 | 7 | 12 | 12 | 0
|  | 2 | 3.24 | MMB- V0d (= MMB-V0b' reassembled w/o RF cap w/ RF wall) ready @ Pton |  |  | 3.23 | [5 empty] | 2019-01-28 | 4 |  | 100% | k | 2019-01-23 | 2019-01-28 | 4 | 6 | 6 | 0
|  | 2 | 3.25 | MMB-V0d results in and warm-up |  |  | 3.24 | [5 empty] | 2019-02-05 | 5 |  | 100% | o | 2019-01-29 | 2019-02-05 | 5 | 8 | 7 | 1
|  | 2 | 3.26 | MMB- V0e (= MMB-V0d reassembled with pogo pins no tripods) ready @ Pton | [12 empty] | k | - | - | - | - | - | -
|  | 2 | 3.27 | MMB-V0e results in and warm-up | [12 empty] | o | - | - | - | - | - | -
|  | 2 | 3.28 | MMB- V0k (using the last of the dummy DC wafers, with the newly-metalexposed RF wafer, and new through chips, using pogo pins directly to the RF wafer exposed metal) ready @ Pton |  |  | 3.27 |  |  |  |  | 2019-02-11 | 2019-03-07 | 4 |  | 100% | k | 2019-02-11 | 2019-03-07 | 4 | 25 | 4 | 21
|  | 2 | 3.29 | MMB-V0k dunk test |  |  | 3.28 | [5 empty] | 2019-03-08 | 5 |  | 100% | o | 2019-03-08 | 2019-03-08 | 5 | 1 | 1 | 0
|  | 2 | 3.28 | More through chips arrive in Princeton | [8 empty] | 2019-02-18 | 1 |  | 100% |  | 2019-02-18 | 2019-02-18 | 1 | 1 | 1 | 0
|  | 2 | 3.29 | NIST reopen | [8 empty] | 2019-01-28 |  |  | 100% |  | 2019-01-28 | 2019-01-28 | 1 | 1 | 1 | 0
|  | 2 | 3.30 | MMB-V1 (= RF v1; mechanical DC; duroid launches; side launch FR) ready&test @ Pton | [7 empty] | 2019-01-28 | 2019-03-29 |  |  |  | o | 2019-01-28 | 2019-03-29 | 44 | 61 | 0 | 61
|  | 3 | 3.30.1 | RF-Duroid layout done (Hannes) | [7 empty] | 2019-01-28 | 2019-02-08 | 3 |  | 100% |  | 2019-01-28 | 2019-02-08 | 3 | 12 | 3 | 9
|  | 3 | 3.30.2 | RF resonator chips fabricated and tested(NIST) | [7 empty] | 2019-01-28 | 2019-03-05 | 13 |  | 100% |  | 2019-01-28 | 2019-03-05 | 13 | 37 | 17 | 20
|  | 3 | 3.30.3 | RF v1 fabricated and arrived at Princeton |  |  |  | 3.30.1 |  |  |  |  | 2019-03-07 | 5 |  | 100% |  | 2019-02-11 | 2019-03-07 | 5 | 25 | 8 | 17
|  | 3 | 3.30.4 | Full set of RF resonators arrived at Princeton | 1 set |  | 3.30.2 | [5 empty] | 2019-03-07 | 1 |  | 100% |  | 2019-03-06 | 2019-03-07 | 1 | 2 | 1 | 1
|  | 3 | 3.30.5 | MMB-v1-Duroid assembled @Pton |  |  |  | 3.30.4 | 3.30.3 |  |  | 2019-03-07 | 2019-03-22 | 4 |  |  |  | 2019-03-07 | 2019-03-22 | 4 | 16 | 0 | 16
|  | 3 | 3.30.6 | MMB-v1-Duroid preliminary tests completed |  |  | 3.30.5 | [6 empty] | 5 |  |  | o | 2019-03-25 | 2019-03-29 | 5 | 5 | 0 | 5
|  | 3 | 3.30.7 | SMuRF full system installed @ Pton | [7 empty] | 2019-03-27 | 2019-04-01 | 1 |  |  |  | 2019-03-27 | 2019-04-01 | 1 | 6 | 0 | 6
|  | 3 | 3.30.8 | MMB-v1-Duroid tests completed |  |  | 3.30.6 | 3.30.7 | [5 empty] | 5 |  |  | o | 2019-04-02 | 2019-04-08 | 5 | 7 | 0 | 7
|  | 2 | 3.31 | MMB-v1 to Cornell to begin magnetic shielding testing sequence |  |  | 3.30.8 | [6 empty] | 1 |  |  | o | 2019-04-09 | 2019-04-09 | 1 | 1 | 0 | 1
|  | 2 | 3.32 | MMB-v1b (= RF v1; screened DC v1; duroid launches; DC flex2) ready&test @ Pton | [7 empty] | 2019-01-28 | 2019-04-17 |  |  |  | o | 2019-01-28 | 2019-04-17 | 57 | 80 | 0 | 80
|  | 3 | 3.32.1 | RF resonator chips fabricated and tested(NIST) | [7 empty] | 2019-03-05 | 2019-03-20 | 13 |  |  |  | 2019-03-05 | 2019-03-20 | 13 | 16 | 0 | 16
|  | 3 | 3.32.2 | RF-v1b fabricated and arrived at Princeton | [8 empty] | 2019-03-21 | 5 |  |  |  | 2019-03-15 | 2019-03-21 | 5 | 7 | 0 | 7
|  | 3 | 3.32.3 | Full set of RF resonators arrived at Princeton | 1 set |  | 3.32.1 | [5 empty] | 2019-03-21 | 1 |  |  |  | 2019-03-21 | 2019-03-21 | 1 | 1 | 0 | 1
|  | 3 | 3.32.4 | DC wafer design | [8 empty] | 2019-03-12 | 5 |  |  |  | 2019-03-06 | 2019-03-12 | 5 | 7 | 0 | 7
|  | 3 | 3.32.5 | DC wafer fabricated (NIST) |  |  |  | 3.32.4 | [5 empty] | 10 |  |  |  | 2019-03-13 | 2019-03-26 | 10 | 14 | 0 | 14
|  | 3 | 3.32.6 | DC wafer screening | Cornell ready for test DC |  | 3.32.5 | [6 empty] | 5 |  |  | g | 2019-03-27 | 2019-04-02 | 5 | 7 | 0 | 7
|  | 3 | 3.32.7 | MMB-v1b assembled @Pton |  |  | 3.32.6 | 3.32.3 | 3.32.2 | 3.49.5 |  |  |  | 4 |  |  |  | 2019-04-05 | 2019-04-10 | 4 | 6 | 0 | 6
|  | 3 | 3.32.8 | MMB-v1b tests completed |  |  | 3.32.7 | [6 empty] | 5 |  |  | o | 2019-04-11 | 2019-04-17 | 5 | 7 | 0 | 7
|  | 2 | 3.33 | MMB-V2 (= RF v2; screened DC v2; RF flex2; DC flex2) ready @ Pton | [7 empty] | 2019-03-01 | 2019-04-29 | 5 |  |  | p | 2019-03-01 | 2019-04-29 | 5 | 60 | 0 | 60
|  | 3 | 3.33.1 | RF launch for flex designed (Karsten) | [8 empty] | 2019-03-01 |  |  |  | k | 2019-03-01 | 2019-03-01 | 1 | 1 | 0 | 1
|  | 3 | 3.33.2 | RF flex launch test | [9 empty] | 5 |  |  |  | - | - | 5 | - | - | -
|  | 4 | 3.33.2.1 | RF flex launch design (Hannes) |  |  | 3.33.1 | [5 empty] | 2019-03-10 | 5 |  | 100% |  | 2019-03-04 | 2019-03-10 | 5 | 7 | 7 | 0
|  | 4 | 3.33.2.2 | RF flex launch fab/arrived Pton |  |  | 3.33.2.1 | [5 empty] | 2019-03-25 | 5 |  |  |  | 2019-03-11 | 2019-03-25 | 5 | 15 | 0 | 15
|  | 4 | 3.33.2.3 | RF flex launch test box deisgn/made |  |  | 3.33.2.1 | [5 empty] | 2019-03-22 | 5 |  | 100% |  | 2019-03-11 | 2019-03-22 | 5 | 12 | 7 | 5
|  | 4 | 3.33.2.4 | RF flex 2v0 received |  |  | 3.33.1 | [5 empty] | 2019-03-21 |  |  |  |  | 2019-03-04 | 2019-03-21 | 14 | 18 | 0 | 18
|  | 4 | 3.33.2.5 | RF flex test | [7 empty] | 2019-03-21 | 2019-04-02 | 5 |  |  |  | 2019-03-21 | 2019-04-02 | 5 | 13 | 0 | 13
|  | 5 | 3.33.2.5.1 | RF flex 2v0 test @ Pton | [7 empty] | 2019-03-21 | 2019-04-04 | 5 |  |  |  | 2019-03-21 | 2019-04-04 | 5 | 15 | 0 | 15
|  | 5 | 3.33.2.5.2 | RF flex 2v0 test @ NIST | [7 empty] | 2019-04-01 | 2019-04-02 |  |  |  |  | 2019-04-01 | 2019-04-02 | 2 | 2 | 0 | 2
|  | 3 | 3.33.3 | RF-v2 (w/flex) layout done (Hannes) |  |  | 3.33.2.5 | [6 empty] | 2 |  |  |  | 2019-04-03 | 2019-04-04 | 2 | 2 | 0 | 2
|  | 3 | 3.33.4 | RF-v2 fabricated (NIST) and arrived to Princeton |  |  | 3.33.3 | [6 empty] | 5 |  |  |  | 2019-04-05 | 2019-04-11 | 5 | 7 | 0 | 7
|  | 3 | 3.33.5 | RF resonator chips design done (uMUX100kv3) | [8 empty] | 2019-03-19 |  |  |  |  | 2019-03-19 | 2019-03-19 | 1 | 1 | 0 | 1
|  | 3 | 3.33.6 | RF resonator chips fabricated and tested(NIST) | 2 sets |  | 3.33.5 | [6 empty] | 13 |  |  |  | 2019-03-20 | 2019-04-05 | 13 | 17 | 0 | 17
|  | 3 | 3.33.7 | Full set of RF resonators arrived at Princeton | 1 set |  | 3.33.6 | [6 empty] | 1 |  |  |  | 2019-04-08 | 2019-04-08 | 1 | 1 | 0 | 1
|  | 3 | 3.33.8 | DC wafer fabricated (NIST) |  |  | 3.32.5 | [6 empty] | 10 |  |  |  | 2019-03-27 | 2019-04-09 | 10 | 14 | 0 | 14
|  | 3 | 3.33.9 | DC wafer screening |  |  | 3.32.5 | 3.32.6 | [5 empty] | 5 |  |  | g | 2019-04-03 | 2019-04-09 | 5 | 7 | 0 | 7
|  | 3 | 3.33.10 | MMB-v2 assembled |  |  | 3.33.4 | 3.32.7 | 3.33.7 | 3.49.5 |  |  |  | 5 |  |  | k | 2019-04-12 | 2019-04-18 | 5 | 7 | 0 | 7
|  | 3 | 3.33.11 | MMB-v2 tests completed @ Pton |  |  | 3.33.10 | 3.32.8 | [5 empty] | 5 |  |  | p | 2019-04-23 | 2019-04-29 | 5 | 7 | 0 | 7
|  | 2 | 3.34 | DC flex 2v0 received | [8 empty] | 2019-03-18 |  |  |  | k | 2019-03-18 | 2019-03-18 | 1 | 1 | 0 | 1
|  | 2 | 3.35 | NIST dummy prototypes to Pton | [8 empty] | 2018-10-23 |  |  | 100% | 100 | 2018-10-23 | 2018-10-23 | 1 | 1 | 1 | 0
|  | 2 | 3.36 | Pin-slot test with MMBv0 | [7 empty] | 2018-12-06 | 2018-12-14 |  |  | 100% | o | 2018-12-06 | 2018-12-14 | 7 | 9 | 9 | 0
|  | 2 | 3.37 | Pin-slot test with MMBv0 with UHF/MF horn |  |  | 3.35 |  |  |  |  | 2018-12-21 | 2018-12-26 |  |  | 100% | o | 2018-12-21 | 2018-12-26 | 2 | 6 | 6 | 0
|  | 2 | 3.38 | Pin-slot test on dummy detector stack with UHF/MF horn @ Pton |  |  | 3.36 | 3.37 |  |  |  | 2018-12-28 | 2019-01-07 |  |  | 100% | o | 2018-12-28 | 2019-01-07 | 6 | 11 | 11 | 0
|  | 2 | 3.39 | Dummy DC wafer @ Cornell |  |  | 3.37 |  |  |  |  | 2018-12-26 | 2019-01-15 |  |  | 100% | g | 2018-12-26 | 2019-01-15 | 13 | 21 | 20 | 1
|  | 2 | 3.40 | Bonding test with Berkeley dummy detector and invar flange | Need 2nd interlocking flange made and receive UCB mech wafers | [6 empty] | 2019-01-11 | 2019-02-12 |  |  | 100% | p | 2019-01-11 | 2019-02-12 | 22 | 33 | 33 | 0
|  | 3 | 3.40.1 | invar interlocking flange (no heat treatment) made | [8 empty] | 2019-01-11 |  |  | 100% | k | 2019-01-11 | 2019-01-11 | 1 | 1 | 1 | 0
|  | 3 | 3.40.2 | dummy LBL det wafer | [8 empty] | 2018-12-26 |  |  | 100% | 2 | 2018-12-26 | 2018-12-26 | 0 | 1 | 0 | 1
|  | 3 | 3.40.3 | LBL wafer assembled and tested |  |  | 3.40.1 | 3.40.2 |  |  |  |  | 2019-01-25 | 3 |  | 100% | k | 2019-01-14 | 2019-01-25 | 3 | 12 | 3 | 9
|  | 3 | 3.40.4 | invar flange cool down @ Mich |  |  | 3.40.3 |  |  |  |  | 2019-01-30 | 2019-02-12 | 5 |  | 100% | p | 2019-01-30 | 2019-02-12 | 5 | 14 | 7 | 7
|  | 2 | 3.41 | MMB-V0-flexm (= MMB-V0 with DC/RF flex attached, mechanical test) ready&test @ Mich | [7 empty] | 2019-01-10 | 2019-02-12 |  |  | 100% | o | 2019-01-10 | 2019-02-12 | 23 | 34 | 34 | 0
|  | 3 | 3.41.1 | RF flex assembled |  |  | 3.19 | [5 empty] | 2019-01-15 |  |  | 100% | k | 2019-01-10 | 2019-01-15 | 4 | 6 | 6 | 0
|  | 3 | 3.41.2 | DC flex assembled |  |  | 3.39 | [8 empty] | 100% | k | 2019-01-16 | 2019-01-16 | 1 | 1 | 1 | 0
|  | 3 | 3.41.3 | Glue flexes to RF wafer |  |  | 3.41.2 | [5 empty] | 2019-01-30 | 1 |  | 100% | k | 2019-01-17 | 2019-01-30 | 1 | 14 | 1 | 13
|  | 3 | 3.41.4 | Heat clamp with two slots | [8 empty] | 2019-01-18 |  |  | 100% | k | 2019-01-18 | 2019-01-18 | 1 | 1 | 1 | 0
|  | 3 | 3.41.5 | Assembled MMB-v0 with flex-RF |  |  | 3.41.4 | 3.39 | 3.41.3 |  |  |  | 2019-01-31 | 1 |  | 100% | k | 2019-01-31 | 2019-01-31 | 1 | 1 | 1 | 0
|  | 3 | 3.41.6 | MMB-v0-flex test @ Mich |  |  | 3.41.5 |  |  |  |  | 2019-01-31 | 2019-02-12 | 5 |  | 100% | o | 2019-01-31 | 2019-02-12 | 5 | 13 | 7 | 6
|  | 2 | 3.42 | MMB-V0-flexm-v1 (= MMB-V0 with DC flexs attached, mechanical test) ready&test @ Mich | [7 empty] | 2019-02-13 | 2019-02-25 |  |  | 100% | o | 2019-02-13 | 2019-02-25 | 8 | 13 | 13 | 0
|  | 3 | 3.42.1 | DC flex assembled |  |  | 3.41.6 |  |  |  |  | 2019-02-13 |  | 1 |  | 100% | k | 2019-02-13 | 2019-02-13 | 1 | 1 | 1 | 0
|  | 3 | 3.42.2 | MMB-v0-flex test @ Mich |  |  | 3.42.1 |  |  |  |  | 2019-02-14 | 2019-02-25 | 5 |  | 100% | o | 2019-02-14 | 2019-02-25 | 5 | 12 | 8 | 4
|  | 2 | 3.43 | MMB-V0-flexm-v2 (= MMB-V0 with DC flexs attached, mechanical test) ready&test @ Mich | [7 empty] | 2019-02-28 | 2019-03-11 |  |  |  | o | 2019-02-28 | 2019-03-11 | 8 | 12 | 0 | 12
|  | 3 | 3.43.1 | DC flex assembled |  |  | 3.41.4 |  |  |  |  | 2019-02-28 |  |  |  | 100% | k | 2019-02-28 | 2019-02-28 | 1 | 1 | 1 | 0
|  | 3 | 3.43.2 | MMB-v0-flex test @ Mich |  |  | 3.43.1 |  |  |  |  | 2019-03-01 | 2019-03-11 |  |  |  | o | 2019-03-01 | 2019-03-11 | 7 | 11 | 0 | 11
|  | 2 | 3.44 | Heat test D0a ready&test @ Mich | [7 empty] | 2019-02-14 | 2019-02-25 |  |  | 100% | o | 2019-02-14 | 2019-02-25 | 7 | 12 | 12 | 0
|  | 3 | 3.44.1 | MMB heat test assembled | [8 empty] | 2019-02-14 | 1 |  | 100% | k | 2019-02-14 | 2019-02-14 | 1 | 1 | 1 | 0
|  | 3 | 3.44.2 | Heat test D0a test @ Mich |  |  | 3.44.1 |  |  |  |  | 2019-02-14 | 2019-02-25 | 5 |  | 100% | o | 2019-02-14 | 2019-02-25 | 5 | 12 | 8 | 4
|  | 2 | 3.45 | Heat test D0a' ready&test @ Mich | [7 empty] | 2019-02-26 | 2019-03-11 |  |  | 100% |  | 2019-02-26 | 2019-03-11 | 10 | 14 | 14 | 0
|  | 3 | 3.45.1 | MMB heat test assembled |  |  | 3.44.2 | [5 empty] | 2019-02-28 |  |  | 100% | k | 2019-02-26 | 2019-02-28 | 3 | 3 | 3 | 0
|  | 3 | 3.45.2 | Heat test D0a' test @ Mich |  |  | 3.45.1 |  |  |  |  | 2019-03-01 | 2019-03-11 |  |  | 100% | o | 2019-03-01 | 2019-03-11 | 7 | 11 | 11 | 0
|  | 2 | 3.46 | 2nd Mechanical NIST detector wafer test on HF/MF horn array | [7 empty] | 2019-03-01 | 2019-03-11 |  |  | 100% |  | 2019-03-01 | 2019-03-11 | 7 | 11 | 11 | 0
|  | 2 | 3.47 | Heat test D0a''(==D0a', add thermometer on horn and DC, copper. Braid btwn HC and MC, mount and MC) ready&test @ Mich | [7 empty] | 2019-03-12 | 2019-03-25 |  |  |  |  | 2019-03-12 | 2019-03-25 | 10 | 14 | 0 | 14
|  | 3 | 3.47.1 | MMB heat test assembled |  |  | 3.45.2 | [5 empty] | 2019-03-15 |  |  |  | k | 2019-03-12 | 2019-03-15 | 4 | 4 | 0 | 4
|  | 3 | 3.47.2 | Heat test D0a'' @ Mich |  |  | 3.47.1 | [6 empty] | 6 |  |  | o | 2019-03-18 | 2019-03-25 | 6 | 8 | 0 | 8
|  | 2 | 3.48 | mich fridge rack move | [7 empty] | 2019-03-13 | 2019-03-15 |  |  |  |  | 2019-03-13 | 2019-03-15 | 3 | 3 | 0 | 3
|  | 2 | 3.49 | Heat test D0b(==D0a'', w/ G10 removed) ready&test @ Mich | [7 empty] | 2019-03-26 | 2019-04-04 |  |  |  |  | 2019-03-26 | 2019-04-04 | 8 | 10 | 0 | 10
|  | 3 | 3.49.1 | MMB heat test assembled |  |  | 3.47.2 | [6 empty] | 1 |  |  | k | 2019-03-26 | 2019-03-26 | 1 | 1 | 0 | 1
|  | 3 | 3.49.2 | RF flex 2v0 test | [7 empty] | 2019-03-21 | 2019-03-22 |  |  |  |  | 2019-03-21 | 2019-03-22 | 2 | 2 | 0 | 2
|  | 4 | 3.49.2.1 | RF flex assembled | [8 empty] | 2019-03-22 |  |  |  | k | 2019-03-22 | 2019-03-22 | 1 | 1 | 0 | 1
|  | 3 | 3.49.3 | Mech-UFM test | [7 empty] | 2019-03-25 | 2019-03-25 |  |  |  |  | 2019-03-25 | 2019-03-25 | 1 | 1 | 0 | 1
|  | 4 | 3.49.3.1 | 2nd Mechanical NIST detector wafer test on HF/MF horn array w/ Al pogo Heat clamp |  |  | 3.33.2.4 |  |  |  |  | 2019-03-25 |  | 1 |  |  | k | 2019-03-25 | 2019-03-25 | 1 | 1 | 0 | 1
|  | 3 | 3.49.4 | MMB-V0-flexm-v3 (= RF with DC 2V0/RF 2V0 flex attached, mechanical test) ready&test @ Mich | [7 empty] | 2019-03-21 | 2019-04-12 |  |  |  |  | 2019-03-21 | 2019-04-12 | 17 | 23 | 0 | 23
|  | 4 | 3.49.4.1 | RF flex assembled | [7 empty] | 2019-03-21 |  | 1 |  |  | k | 2019-03-21 | 2019-03-21 | 1 | 1 | 0 | 1
|  | 4 | 3.49.4.2 | DC flex assembled | [7 empty] | 2019-03-21 |  | 3 |  |  | k | 2019-03-21 | 2019-03-25 | 3 | 5 | 0 | 5
|  | 3 | 3.49.5 | Heat test D0b test +RF-flex box + Mech-UFM + MMB-V0-flexm-v3@ Mich |  |  | 3.49.1 | [6 empty] | 7 |  |  | o | 2019-03-27 | 2019-04-04 | 7 | 9 | 0 | 9
|  | 2 | 3.50 | Heat test D0c(no G10, thermometer on HC, Braid btwn mount and MC, pogo pin HC) ready&test @ Mich | [7 empty] | 2019-04-05 | 2019-04-12 |  |  |  |  | 2019-04-05 | 2019-04-12 | 6 | 8 | 0 | 8
|  | 3 | 3.50.1 | MMB heat test assembled |  |  | 3.49.5 | [6 empty] | 3 |  |  | k | 2019-04-05 | 2019-04-09 | 3 | 5 | 0 | 5
|  | 3 | 3.50.2 | Heat test D0c test @ Mich |  |  | 3.50.1 | [6 empty] | 3 |  |  | o | 2019-04-10 | 2019-04-12 | 3 | 3 | 0 | 3
|  | 2 | 3.51 | 3 coax chain installed in Pton | [7 empty] | 2019-02-18 |  | 1 |  | 100% | p | 2019-02-18 | 2019-02-18 | 1 | 1 | 1 | 0
|  | 2 | 3.52 | 3 new chains tested in Pton (single-mux-box) |  |  | 3.51 |  |  |  |  | 2019-02-18 | 2019-02-18 | 1 |  | 100% | p | 2019-02-18 | 2019-02-18 | 1 | 1 | 1 | 0
|  | 2 | 3.53 | Pton DR move | [8 empty] | 2019-03-05 | 2 |  | 100% | p | 2019-03-04 | 2019-03-05 | 2 | 2 | 2 | 0
|  | 2 | 3.54 | Install old 1-chain from Pton DR into Michigan DR | [8 empty] | 2019-03-11 | 1 |  |  | o | 2019-03-11 | 2019-03-11 | 1 | 1 | 0 | 1
|  | 2 | 3.55 | Oxford service | [7 empty] | 2019-03-12 | 2019-03-15 |  |  |  | k | 2019-03-12 | 2019-03-15 | 4 | 4 | 0 | 4
|  | 2 | 3.56 | Mich fridge rack move | [7 empty] | 2019-03-12 | 2019-03-13 |  |  |  | o | 2019-03-12 | 2019-03-13 | 2 | 2 | 0 | 2
|  | 2 | 3.57 | READOUT PRR |  |  | 3.33.11 | [6 empty] | 5 |  |  | b | 2019-04-30 | 2019-05-07 | 5 | 8 | 0 | 8
|  | 2 | 3.58 | First UFM-v0 with prototype MF detector array and MMB v1b | [7 empty] | 2019-01-07 | 2019-05-20 |  |  |  |  | 2019-01-07 | 2019-05-20 | 91 | 134 | 0 | 134
|  | 3 | 3.58.1 | First UHF/MF feedhorn array @ Pton | actual date earlier | [6 empty] | 2019-01-07 |  | 1 |  |  |  | 2019-01-07 | 2019-01-07 | 1 | 1 | 0 | 1
|  | 3 | 3.58.2 | MF detector design finalized | actual date earlier | [6 empty] | 2018-12-15 |  | 1 |  |  |  | 2018-12-15 | 2018-12-15 | 1 | 1 | 0 | 1
|  | 3 | 3.58.3 | MF detector array fab finished | [7 empty] | 2019-01-28 |  | 10 |  |  |  | 2019-01-28 | 2019-02-08 | 10 | 12 | 0 | 12
|  | 3 | 3.58.4 | UFM-v0 assembled @ Pton | w/ time to extract MMB-v1b |  | 3.32.8 | 3.58.3 | 3.58.1 |  |  |  |  | 5 |  |  |  | 2019-04-18 | 2019-04-26 | 5 | 9 | 0 | 9
|  | 3 | 3.58.5 | UFM-v0 preliminary testing complete |  |  | 3.58.4 | [6 empty] | 5 |  |  | o | 2019-04-29 | 2019-05-03 | 10 | 5 | 0 | 5
|  | 3 | 3.58.6 | UFM-v0 detailed dark/efficiency testing complete |  |  | 3.58.5 | [6 empty] | 5 |  |  | o | 2019-05-07 | 2019-05-13 | 5 | 7 | 0 | 7
|  | 3 | 3.58.7 | UFM-v0 @ UCSD |  |  | 3.58.6 | [6 empty] | 5 |  |  |  | 2019-05-14 | 2019-05-20 | 5 | 7 | 0 | 7
|  | 3 | 3.58.8 | UFM-v0 optical testing @ UCSD complete |  |  | 3.58.7 | [6 empty] | 14 |  |  | r | 2019-05-21 | 2019-06-10 | 5 | 21 | 0 | 21
|  | 2 | 3.59 | MF DETECTOR PRR |  |  | 3.58.6 | [6 empty] | 5 |  |  |  | 2019-05-14 | 2019-05-20 | 5 | 7 | 0 | 7
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
Formulas:
Monthly = IF(N13<>"",N13,IF([Display:]=" - "," - ",IF(O13<>"",WORKDAY.INTL([Display:],O13-1,weekend,holidays),[Display:]+MAX(P13,1)-1)))
Show Weekends (Daily view only)
Note on D6: Project Start Date Enter the Start Date for the Project. Avoid choosing a date that falls on a Saturday or Sunday.
Note on S6: Daily / Weekly / Monthly: Use this to change the gantt chart view to Weekly or Monthly if you want to see a larger range of dates. Note that the monthly view results in a loss of detail.
Note on S7: Display Week / Display Month: Use this to change the starting week or month shown in the gantt chart.
Note on D8: Today's Date: Use the formula =TODAY() to make the red line in the gantt chart display the current day, or enter the date manually.
Note on D9: Today's Date: Use the formula =TODAY() to make the red line in the gantt chart display the current day, or enter the date manually.
Note on C10: WBS Level: Choose the WBS (Work Breakdown Structure) level from the drop-down in this column.
Note on D10: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to automatically update the numbering.
Note on E10: Task Description Enter the name of each task and sub-task. The task description is automatically indented using conditional formatting based on the WBS Level column.
Note on F10: Task Lead Enter the name of the Task Lead in this column.
Note on H10: Predecessor Tasks: You may use this column to calculate the start date for the task based on the end date of the Predecessor you reference. Use a formula like =A13 to reference the WBS of the Predecessor task that must be completed before this task can start. You can also enter the WBS as a text value by entering an apostrophe before the number like '2.3. Avoid circular references, such as choosing the current task as its own Predecessor. Using this column assumes that you want the task to start on the next work day. See the Help worksheet for more examples of using formulas to create task dependencies.
Note on M10: Start Date You can manually enter the Start date for each task, use the Predecessor column to have a Start date calculated automatically, or use a formula to create a dependency on some other cell. See the Help worksheet for examples of creating dependencies.
Note on N10: End Date If you want to define the End date instead of calculating what it should be, enter the date in this column. Otherwise, enter a value in the Work Days or Calendar Days column to define the duration of the task.
Note on O10: Work Days Enter the number of Work Days that you estimate this task will require to complete. Work Days exclude the weekend (defined in the Help worksheet) and the holidays listed in the Holidays worksheet.
Note on P10: Duration: Calendar Days If you want to enter the number of calendar days instead of the number of work days, enter a value in this column.
Note on Q10: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on R10: Color (Optional): Enter a color code in this column to change the color of the incomplete portion of the gantt chart. 1 - 6 = theme-based accent colors k = black r = red o = orange y = yellow p = purple g = green
Note on S10: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1,holidays) to set the Start date to the next work day (excluding weekends and holidays), where enddate is the cell reference for the End date of the Predecessor task.
Note on T10: End Date The WORKDAY() function is used to calculate the ending date so that the End Date does not fall on a weekend or a holiday. If you choose to use the Duration as the input, the End date is calculated as the Start date + Duration - 1.
Note on U10: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on V10: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on W10: Calendar Days Complete [ You can hide this column prior to printing ] This column is calculated by multiplying the Work Days by the %Complete and using the WORKDAY() function to determine how many calendar days have been completed. Note: The conditional formatting used to create the gantt chart references this column.
Note on X10: Calendar Days Remaining [ You can hide this column prior to printing ] This column is calculated by subtracting the Days Complete from the Duration.
Note on Y10: Planned Start & End After creating the project schedule, you can copy the Start and End columns and use Paste Special > Values to paste the dates into the Planned Start and Planned End columns. The planned periods will be represented in the gantt chart using cross-hatching.

## Holidays
Holidays to Exclude from Work Days
List special dates that should be considered non-working days.
If your project spans more than one year, add separate dates for each holiday for each year.
Date | Description | Country
2015-12-25 | Christmas
2016-12-25 | Christmas
2017-12-25 | Christmas
2018-12-25 | Christmas
2019-12-25 | Christmas
2020-12-25 | Christmas
2021-12-25 | Christmas
2022-12-25 | Christmas
2023-12-25 | Christmas
2024-12-25 | Christmas
2025-12-25 | Christmas
2015-01-01 | New Year's Day
2016-01-01 | New Year's Day
2017-01-01 | New Year's Day
2018-01-01 | New Year's Day
2019-01-01 | New Year's Day
2020-01-01 | New Year's Day
2021-01-01 | New Year's Day
2022-01-01 | New Year's Day
2023-01-01 | New Year's Day
2024-01-01 | New Year's Day
2025-01-01 | New Year's Day
2015-10-12 | Columbus Day | US
2016-10-10 | Columbus Day | US
2017-10-09 | Columbus Day | US
2018-10-08 | Columbus Day | US
2019-10-14 | Columbus Day | US
2020-10-12 | Columbus Day | US
2021-10-11 | Columbus Day | US
2022-10-10 | Columbus Day | US
2023-10-09 | Columbus Day | US
2024-10-14 | Columbus Day | US
2025-10-13 | Columbus Day | US
2015-07-04 | Independence Day | US
2016-07-04 | Independence Day | US
2017-07-04 | Independence Day | US
2018-07-04 | Independence Day | US
2019-07-04 | Independence Day | US
2020-07-04 | Independence Day | US
2021-07-04 | Independence Day | US
2022-07-04 | Independence Day | US
2023-07-04 | Independence Day | US
2024-07-04 | Independence Day | US
2025-07-04 | Independence Day | US
2015-09-07 | Labor Day | US
2016-09-05 | Labor Day | US
2017-09-04 | Labor Day | US
2018-09-03 | Labor Day | US
2019-09-02 | Labor Day | US
2020-09-07 | Labor Day | US
2021-09-06 | Labor Day | US
2022-09-05 | Labor Day | US
2023-09-04 | Labor Day | US
2024-09-02 | Labor Day | US
2025-09-01 | Labor Day | US
2015-01-19 | M.L.King Jr. Day | US
2016-01-18 | M.L.King Jr. Day | US
2017-01-16 | M.L.King Jr. Day | US
2018-01-15 | M.L.King Jr. Day | US
2019-01-21 | M.L.King Jr. Day | US
2020-01-20 | M.L.King Jr. Day | US
2021-01-18 | M.L.King Jr. Day | US
2022-01-17 | M.L.King Jr. Day | US
2023-01-16 | M.L.King Jr. Day | US
2024-01-15 | M.L.King Jr. Day | US
2025-01-20 | M.L.King Jr. Day | US
2015-05-25 | Memorial Day | US
2016-05-30 | Memorial Day | US
2017-05-29 | Memorial Day | US
2018-05-28 | Memorial Day | US
2019-05-27 | Memorial Day | US
2020-05-25 | Memorial Day | US
2021-05-31 | Memorial Day | US
2022-05-30 | Memorial Day | US
2023-05-29 | Memorial Day | US
2024-05-27 | Memorial Day | US
2025-05-26 | Memorial Day | US
2015-02-16 | Presidents Day | US
2016-02-15 | Presidents Day | US
2017-02-20 | Presidents Day | US
2018-02-19 | Presidents Day | US
2019-02-18 | Presidents Day | US
2020-02-17 | Presidents Day | US
2021-02-15 | Presidents Day | US
2022-02-21 | Presidents Day | US
2023-02-20 | Presidents Day | US
2024-02-19 | Presidents Day | US
2025-02-17 | Presidents Day | US
2015-11-26 | Thanksgiving | US
2016-11-24 | Thanksgiving | US
2017-11-23 | Thanksgiving | US
2018-11-22 | Thanksgiving | US
2019-11-28 | Thanksgiving | US
2020-11-26 | Thanksgiving | US
2021-11-25 | Thanksgiving | US
2022-11-24 | Thanksgiving | US
2023-11-23 | Thanksgiving | US
2024-11-28 | Thanksgiving | US
2025-11-27 | Thanksgiving | US
2015-11-11 | Veterans Day | US
2016-11-11 | Veterans Day | US
2017-11-11 | Veterans Day | US
2018-11-11 | Veterans Day | US
2019-11-11 | Veterans Day | US
2020-11-11 | Veterans Day | US
2021-11-11 | Veterans Day | US
2022-11-11 | Veterans Day | US
2023-11-11 | Veterans Day | US
2024-11-11 | Veterans Day | US
2025-11-11 | Veterans Day | US
2015-12-26 | Boxing Day | UK
2016-12-26 | Boxing Day | UK
2017-12-26 | Boxing Day | UK
2018-12-26 | Boxing Day | UK
2019-12-26 | Boxing Day | UK
2020-12-26 | Boxing Day | UK
2021-12-26 | Boxing Day | UK
2022-12-26 | Boxing Day | UK
2023-12-26 | Boxing Day | UK
2024-12-26 | Boxing Day | UK
2025-12-26 | Boxing Day | UK
2015-04-03 | Good Friday | UK
2016-03-25 | Good Friday | UK
2017-04-14 | Good Friday | UK
2018-03-30 | Good Friday | UK
2019-04-19 | Good Friday | UK
2020-04-10 | Good Friday | UK
2021-04-02 | Good Friday | UK
2022-04-15 | Good Friday | UK
2023-04-07 | Good Friday | UK
2024-03-29 | Good Friday | UK
2025-04-18 | Good Friday | UK
2015-04-06 | Easter Monday | UK
2016-03-28 | Easter Monday | UK
2017-04-17 | Easter Monday | UK
2018-04-02 | Easter Monday | UK
2019-04-22 | Easter Monday | UK
2020-04-13 | Easter Monday | UK
2021-04-05 | Easter Monday | UK
2022-04-18 | Easter Monday | UK
2023-04-10 | Easter Monday | UK
2024-04-01 | Easter Monday | UK
2025-04-21 | Easter Monday | UK
2015-05-04 | Early May Bank Holiday | UK
2016-05-02 | Early May Bank Holiday | UK
2017-05-01 | Early May Bank Holiday | UK
2018-05-07 | Early May Bank Holiday | UK
2019-05-06 | Early May Bank Holiday | UK
2020-05-04 | Early May Bank Holiday | UK
2021-05-03 | Early May Bank Holiday | UK
2022-05-02 | Early May Bank Holiday | UK
2023-05-01 | Early May Bank Holiday | UK
2024-05-06 | Early May Bank Holiday | UK
2025-05-05 | Early May Bank Holiday | UK
2015-05-25 | Spring Bank Holiday | UK
2016-05-30 | Spring Bank Holiday | UK
2017-05-29 | Spring Bank Holiday | UK
2018-05-28 | Spring Bank Holiday | UK
2019-05-27 | Spring Bank Holiday | UK
2020-05-25 | Spring Bank Holiday | UK
2021-05-31 | Spring Bank Holiday | UK
2022-05-30 | Spring Bank Holiday | UK
2023-05-29 | Spring Bank Holiday | UK
2024-05-27 | Spring Bank Holiday | UK
2025-05-26 | Spring Bank Holiday | UK
2015-08-03 | Summer Bank Holiday | UK
2016-08-01 | Summer Bank Holiday | UK
2017-08-07 | Summer Bank Holiday | UK
2018-08-06 | Summer Bank Holiday | UK
2019-08-05 | Summer Bank Holiday | UK
2020-08-03 | Summer Bank Holiday | UK
2021-08-02 | Summer Bank Holiday | UK
2022-08-01 | Summer Bank Holiday | UK
2023-08-07 | Summer Bank Holiday | UK
2024-08-05 | Summer Bank Holiday | UK
2025-08-04 | Summer Bank Holiday | UK
2015-08-31 | Late Summer Bank Holiday | UK
2016-08-29 | Late Summer Bank Holiday | UK
2017-08-28 | Late Summer Bank Holiday | UK
2018-08-27 | Late Summer Bank Holiday | UK
2019-08-26 | Late Summer Bank Holiday | UK
2020-08-31 | Late Summer Bank Holiday | UK
2021-08-30 | Late Summer Bank Holiday | UK
2022-08-29 | Late Summer Bank Holiday | UK
2023-08-28 | Late Summer Bank Holiday | UK
2024-08-26 | Late Summer Bank Holiday | UK
2025-08-25 | Late Summer Bank Holiday | UK

## Help
HELP
Version: Gantt Chart Template 4.0 for Excel 2010 or Later (Desktop versions)
| If this page does not answer your questions, visit the following page: | Support
Intro
This Gantt chart spreadsheet is designed to to help you create a simple project schedule. You
only need to know some basic spreadsheet operations, such as how to insert, delete, copy and
and paste rows and cells. For more advanced uses, such as defining task dependencies, you
will need to know how to enter formulas.
New in Version 4.0
- Choose the WBS Level from a drop-down to update the WBS numbering and automatically indent the Task description.
- How you define the task start date and duration is greatly simplified and much more intuitive.
- The information in the header is positioned to allow you to hide columns that you do not need to see.
Getting Started Tips
Watch the Demo Videos
| • Edit the cells with the light green background. | Input Cell
| • Edit the [ Bracketed Text ] in the header (the project title and sub-title). | Input Cell
| • Edit cells within gray borders in the header and in the Holidays worksheet. | Input Cell
| • Some of the labels include cell comments (little red triangles) to provide extra information. | Label
• The project Start date in the header determines the first week shown in the gantt chart.
• Instead of changing the project Start date, use the slider bar to adjust the range of dates
shown in the gantt chart.
• The vertical red line in the gantt chart represents the date in the Today cell.
You can enter the date for Today manually or use the formula =TODAY()
• To insert new tasks, insert a new row, then with the new row selected, press Ctrl+d to copy
the formulas and formatting from the row immediately above the one you selected.
• If you see "#####" in a cell, widen the column to display the cell contents.
• Backup your file regularly to avoid losing data! Excel files DO get corrupted occasionally.
Changing the Display Mode from Daily to Weekly to Monthly
Use the drop-down field to change the display of the gantt chart to daily, weekly, or monthly.
NOTE: When using the monthly view, the length of the bar in the gantt chart does not
represent a true relative duration because each month has a different number of days, and
each column shows a 4-day period (except for the last column in the month, which is variable).
Note: Changing the display may require a few seconds for Excel to recalculate the worksheet.
Edit the WBS Numbering
Use the WBS Level column to choose the outline level for the WBS numbering.
A formula in the WBS column will automatically update the WBS number. The Task Description
is also indented using conditional formatting based on the WBS Level.
If you leave a blank cell above a WBS number, the numbering will reset to 1. The formulas are meant for convenience, but you can manually enter them if you need to. If you manually enter
WBS numbers, then you may need to enter them as text by preceding the number with an
apostrophe, such as '2. Just remember that if you enter them manually, the WBS Level
column cannot be used to change them.
Changing the WEEKEND days
Weekend
| Choose an option or enter a weekend string → | 0000011
| The WORKDAYS.INTL() and NETWORKDAYS.INTL() functions used in this template allow you | Option | Non-Work Days
| to specify which day(s) of the week should be considered the "weekend" or non-working days. | 1 | Saturday, Sunday
|  | 2 | Sunday, Monday
| To use these functions, choose an option from the Weekend drop-down box on the right. | 3 | Monday, Tuesday
|  | 4 | Tuesday, Wednesday
| If one of the options to the right does not work for you, you can enter a string of | 5 | Wednesday, Thursday
| 7 characters, using a "1" to represent a non-workday and a "0" to represent | 6 | Thursday, Friday
| a work day, beginning with Monday. | 7 | Friday, Saturday
|  | 11 | Sunday Only
| For example, the string 0000011 would result in a Saturday-Sunday weekend. | 12 | Monday Only
|  | 13 | Tuesday Only
| Use the Holidays worksheet to include specific dates as non-working days. | 14 | Wednesday Only
|  | 15 | Thursday Only
|  | 16 | Friday Only
|  | 17 | Saturday Only
Change Dates to dd/mm/yyyy Format |  | Date Format
| If you would like to display dates in the gantt chart in UK format (dd/mm/yyyy) choose the | mdy
appropriate option to the right.
Add Rows (Insert New Tasks)
There are many ways to add more tasks. Most importantly, you need to remember to copy
formulas and formatting for the entire row when adding new rows. If you insert a row
between two tasks, the formatting is automatically copied, but you need to copy formulas.
Below are the recommended ways to add new rows.
Note: Use row operations by right-clicking on the Row #
Method 1: Insert a Row then Copy Formulas Down
1. Right-click on a row and select "Insert" (This inserts a row ABOVE the selected row)
2. Press Ctrl+d to copy formulas and formatting from the row above the new one.
3. Edit the green cells in your newly inserted row.
Method 2: Copy a Row down using the selection drag handle
Note: After inserting a row, you can select the row above it and use the selection drag
handle to copy the row down. This is also how you can easily add rows at the bottom.
The screenshot on the right shows the
selection drag handle for a selected row.
Method 3: Copy a Row and Insert the Copied Row
1. Right-click on a row and select "Copy"
2. Right-click on a row and select "Insert Copied Cells"
3. Edit the green cells in your newly inserted row.
Note: This method is not preferred because it can result in a messy set of conditional
formatting rules. Inserting rows and then copying down via Ctrl+d or using the drag handle
is the preferred method.
Delete a Row (Remove a Task)
Right-click on the row number of the row you want to delete and select Delete.
If this results in errors, then you probably had formulas that referenced cells in the deleted row.
Press CTRL+z to Undo, or search for #REF! errors and fix them.
Move a Row
You can move a row using cut & paste. First, right-click on the row number and select "Cut".
Then, right-click on a different row number and select "Insert Cut Cells" - this will insert the cut
row above the new row you have selected.
Create Task Dependencies
You can use Excel formulas to make tasks adjust based on the start or end of another task.
Normally, a task dependency is used to define the start date to be the day after the end date
of a prior task. The prior task is called the "predecessor." Below are a few different ways that
you can create task dependencies using Excel formulas.
Method 1: Creating Your Own Formulas
Entering your own formulas allows you to do whatever you want, but may be more difficult. Also, it may not be easy for somebody else to identify your task dependencies.
A. Reference the project Start date (e.g. =$C$4 )
B. Set the Start date to the next Work Day after another task's End date.
- Use the formula =WORKDAY.INTL(enddate,1,weekend,holidays) where enddate is the reference to the End date of a predecessor task.
- For multiple predecessors, the formula would be
=WORKDAY.INTL(MAX(enddate1,enddate2,enddate3),1,weekend,holidays)
C. Set the Start date to the next Calendar Day after another task's End date.
- This formula is very simple: =enddate+1
- For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3)+1
D. Set the Start date to a number of Work days before or after another date.
- This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY.INTL(startdate,-5,weekend,holidays)
Note: Refer to Excel's Help system to learn more about the WORKDAY() and WORKDAY.INTL() functions.
Method 2: Using the Predecessor Columns
The Predecessor columns make it easy to create a task dependency where the Start date is the next Work Day after a predecessor's end date. To use the Predecessor columns, you must enter the WBS for the predecessor task using a formula or as text.
A. Reference a Predecessor using a formula.
In the predecessor column, press "=" and then click on the cell containing the WBS that you want to reference. Then press Enter. This is the preferred method.
B. Enter the Predecessor manually as text.
You can enter the Predecessor manually, but you must make sure that you enter it as text, or you will end up with a bunch of #NA errors. To enter 1.3 as text, just add an apostrophe at the beginning like this: '1.3.
Note: This is not the best method, because if you insert a new task, you'll have to update all of the Predecessors again, or at least verify that they are still correct.
Multiple Predecessors
The worksheet contains 3 Predecessor columns, but two are hidden by default. If you want to use more than 1 predecessor, unhide the hidden columns.
Change the End Date Font to Red when Behind Schedule
|  | Feature on/off: | off
Conditional formatting can be used to do some very useful things. One feature built into this
spreadsheet is the option to change the font color of the End date to red when it is approaching
the current date and also make it bold when the task is past due (if % Done is less than 100%).
| Change the urgency days to the right to determine when the End date will change to red. | Urgency days: | 7
Start the Week on Sunday instead of Monday
The option to the right will allow you to choose to display the work week starting with Sunday instead of Monday. This affects the chart display only, not any other work day formulas.
|  | Start Day: | Monday | 2
Show/Hide Weekends in Daily View
The option to the right will allow you to show or hide weekends in the Daily view of the Gantt chart. The chart will skip the days you have specified as weekend days.
|  | Show Weekends: | TRUE
Color-Coding the Bars of the Gantt Chart
The Color (Clr) column allows you to change the color of the bar in the gantt chart.
The default color is blue, but you can enter the following letters or numbers to change the color:
k (black), r (red), o (orange), y (yellow), p (purple), g (green), 1 - 6 (theme-based accent colors)
Note: The color affects only the INCOMPLETE portion of the bar. The complete portion of the bar
will always be gray.
Advanced Uses of the Color Column
| Use a Formula to Show Urgency |  | Urgency (Days)
| You can enter a formula in the Color column to change the color to orange based on a | red | 2
| comparison of the End date and Today's date. For example, the following formula would give | orange | 14
| you a 10-day warning, where end_date is a reference to the End date cell. | yellow | 28
=IF(end_date<TODAY()+10,"o","")
The following formula makes the 10-day warning orange and a 2-day warning red.
=IF(end_date<TODAY()+2,"r",IF(end_date<TODAY()+10,"o",""))
The fancy formula below makes use of the table of urgency values to the right. Note that "urgency_days" is a named range referring to the table on the right.
=IF(end_date<TODAY()+INDEX(urgency_days,1),"r", IF(end_date<TODAY()+ INDEX(urgency_days,2),"o",IF(end_date<TODAY()+ INDEX(urgency_days,3),"y","")))
| Color-Code Based on Lead Name | Names | Color
| One popular reason for color-coding is to help identify ownership of a task. To do this, | Bob | 1
| you could create your own nested IF formula: =IF(ref="Bob","o",If(ref="Sally","p","")) | Sarah | 2
| where "ref" is the reference to the cell in the Lead column. | Bill | 3
|  | Jim | 4
| If you want to use the table listed to the right of this help section, you can edit the following |  | 5
| formula in the Color column. Note that the Names must match exactly. |  | 6
| =IFERROR( INDEX( lead_color, MATCH( ref, lead_names, 0) ), "") |  | p
g
k
r
o
y
Frequently Asked Questions
Q: | How do I make a Summary task show the MIN(start) and MAX(end) for a group of sub-tasks?
This can be done by entering =MIN(startdates) for the Start date and =MAX(enddates) for the End date, where startdates and enddates are references to the range of start dates and end dates for the group of sub tasks.
Q: | How do I display or "unhide" hidden rows or columns?
To display a hidden row, select the row above and below the rows you want to display.
Right-click on one of the selected row numbers and then choose Unhide.
Q: | My project spans 2-3 years. How do I print the entire chart without scrolling?
If the monthly view is not sufficient to display the entire project span, you will need to add more
columns to the right side of the gantt chart. See the video on the support page:
View the Video
Q: | How do I use Grouping?
You can expand or collapse a group of rows using Excel's "Group and Outline" feature.
To define a group of rows, select the rows and go to Data > Group.
Q: | How do I change the Print Area and Settings?
Select the entire range of cells you want to print and go to Page Layout > Print Area > Set Print Area
Open the Page Setup dialog box to adjust the Scaling, such as fitting to 1 page wide.
Q: | Can I add more color codes or change the existing colors?
Yes (though not easily). You'll need to create your own set of conditional formats. If you have made
a lot of changes, the set of conditional formats can get pretty messed up, so look at a fresh
copy of this template to see how the conditional formats are set up. Go to Conditional Formatting
and select Manage Rules and choose This Worksheet from the drop-down.
Q: | How do I calculate the %Complete for an entire category of tasks?
The %Complete for a category task can be calculated from its sub tasks using the formula below, where "workdays_range" is a reference to the range of work day values and "complete_range" is a reference to the %complete for each of the sub tasks.
=SUMPRODUCT(workdays_range,complete_range)/SUM(workdays_range)
Example: =SUMPRODUCT(O18:O25,K18:K25)/SUM(O18:O25)
Let's say you have 3 sub tasks that are 10 days, 12 days, and 14 days long, respectively. If the first subtask is 50% complete and the others are 25% complete, you could calculate the overall percent complete for the group as: =(10*50%+12*25%+14*25%)/(10+12+14).
Q: | How do I calculate the % Complete for a level 1 task that contains other summary tasks?
If WBS 1.2 is calculating the % Complete for its own set of sub tasks, 1.2.1, 1.2.2, 1.2.3, etc.
then when calculating the overall % Complete for the top-level 1 task, you would need to exclude
task 1.2's sub tasks, or risk double-counting them. The % Complete formula for the level 1 task
would get complicated, so the easiest thing is to avoid calculating the % Complete for task 1.2.
For task 1.2, you can still use MIN() and MAX() for the start and end dates, but delete the
formula for the % Complete.
The following is an example of a Level 1 task that calculates the % Complete for a non-contiguous
range of tasks:
= ( SUMPRODUCT(days1, pdone1) + SUMPRODUCT(days2, pdone2) ) / SUM(days1, days2)
where days1, days2, pdone1 and pdone2 are references to ranges of cells in the Work Days
and % Done columns.
© 2006-2016 Vertex42 LLC
Note on C22: This is an example comment.

## TermsOfUse
Terms of Use
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
By Vertex42.com
© 2006-2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet. If necessary, you may hide it by right-clicking on the tab and selecting Hide.

## GanttChart-v0
|  |  |  | Gantt Chart | [9 empty] | © 2006-2017 Vertex42.com |  |  | [Hide this row]
WBS 1.5 Gantt Chart for Detector & Readout Production & Validation, Simons Observatory
|  |  |  | Project Lead: Suzanne Staggs |  | Editor: Patty Ho
|  |  |  | Start: | 2018-11-19 | [12 empty] | Display: | Monthly
|  |  |  | End: | 2020-12-14 | [12 empty] | Month: | 1
|  |  |  | Today: | 2019-03-25 | [17 empty] | [42] | time axis 2018-11-01 to 2023-02-25
|  |  | WBS Level | WBS | Task | Note | Total Counts | Predecessors |  |  |  | Actual Start | Actual End | Work Days | Cal Days | % Done | Color | Actual Start | Actual End | Work Days | Cal Days | Days Done | Days Left | Planned Start | Planned End |  | 2018-11-01: 2018-11-01; 2018-12-01: 2018-12-01; 2019-01-01: 2019-01-01; 2019-02-01: 2019-02-01; 2019-03-01: 2019-03-01; 2019-04-01: 2019-04-01; 2019-05-01: 2019-05-01; 2019-06-01: 2019-06-01; 2019-07-01: 2019-07-01; 2019-08-01: 2019-08-01; 2019-09-01: 2019-09-01; 2019-10-01: 2019-10-01; 2019-11-01: 2019-11-01; 2019-12-01: 2019-12-01; 2020-01-01: 2020-01-01; 2020-02-01: 2020-02-01; 2020-03-01: 2020-03-01; 2020-04-01: 2020-04-01; 2020-05-01: 2020-05-01; 2020-06-01: 2020-06-01; 2020-07-01: 2020-07-01; 2020-08-01: 2020-08-01; 2020-09-01: 2020-09-01; 2020-10-01: 2020-10-01; 2020-11-01: 2020-11-01; 2020-12-01: 2020-12-01; 2021-01-01: 2021-01-01; 2021-02-01: 2021-02-01; 2021-03-01: 2021-03-01; 2021-04-01: 2021-04-01; 2021-05-01: 2021-05-01; 2021-06-01: 2021-06-01; 2021-07-01: 2021-07-01; 2021-08-01: 2021-08-01; 2021-09-01: 2021-09-01; 2021-10-01: 2021-10-01; 2021-11-01: 2021-11-01; 2021-12-01: 2021-12-01; 2022-01-01: 2022-01-01; 2022-02-01: 2022-02-01; 2022-03-01: 2022-03-01; 2022-04-01: 2022-04-01; 2022-05-01: 2022-05-01; 2022-06-01: 2022-06-01; 2022-07-01: 2022-07-01; 2022-08-01: 2022-08-01; 2022-09-01: 2022-09-01; 2022-10-01: 2022-10-01; 2022-11-01: 2022-11-01; 2022-12-01: 2022-12-01; 2023-01-01: 2023-01-01; 2023-02-01: 2023-02-01
[27 empty] | 2018-11-01 | [6 empty] | 2018-12-01 | [6 empty] | 2019-01-01 | [6 empty] | 2019-02-01 | [6 empty] | 2019-03-01 | [6 empty] | 2019-04-01 | [6 empty] | 2019-05-01 | [6 empty] | 2019-06-01 | [6 empty] | 2019-07-01 | [6 empty] | 2019-08-01 | [6 empty] | 2019-09-01 | [6 empty] | 2019-10-01 | [6 empty] | 2019-11-01 | [6 empty] | 2019-12-01 | [6 empty] | 2020-01-01 | [6 empty] | 2020-02-01 | [6 empty] | 2020-03-01 | [6 empty] | 2020-04-01 | [6 empty] | 2020-05-01 | [6 empty] | 2020-06-01 | [6 empty] | 2020-07-01 | [6 empty] | 2020-08-01 | [6 empty] | 2020-09-01 | [6 empty] | 2020-10-01 | [6 empty] | 2020-11-01 | [6 empty] | 2020-12-01 | [6 empty] | 2021-01-01 | [6 empty] | 2021-02-01 | [6 empty] | 2021-03-01 | [6 empty] | 2021-04-01 | [6 empty] | 2021-05-01 | [6 empty] | 2021-06-01 | [6 empty] | 2021-07-01 | [6 empty] | 2021-08-01 | [6 empty] | 2021-09-01 | [6 empty] | 2021-10-01 | [6 empty] | 2021-11-01 | [6 empty] | 2021-12-01 | [6 empty] | 2022-01-01 | [6 empty] | 2022-02-01 | [6 empty] | 2022-03-01 | [6 empty] | 2022-04-01 | [6 empty] | 2022-05-01 | [6 empty] | 2022-06-01 | [6 empty] | 2022-07-01 | [6 empty] | 2022-08-01 | [6 empty] | 2022-09-01 | [6 empty] | 2022-10-01 | [6 empty] | 2022-11-01 | [6 empty] | 2022-12-01 | [6 empty] | 2023-01-01 | [6 empty] | 2023-02-01
Name | Parameter | Value | [24 empty] | 2018-11-01: 1; 2018-12-01: 2; 2019-01-01: 3; 2019-02-01: 4; 2019-03-01: 5; 2019-04-01: 6; 2019-05-01: 7; 2019-06-01: 8; 2019-07-01: 9; 2019-08-01: 10; 2019-09-01: 11; 2019-10-01: 12; 2019-11-01: 13; 2019-12-01: 14; 2020-01-01: 15; 2020-02-01: 16; 2020-03-01: 17; 2020-04-01: 18; 2020-05-01: 19; 2020-06-01: 20; 2020-07-01: 21; 2020-08-01: 22; 2020-09-01: 23; 2020-10-01: 24; 2020-11-01: 25; 2020-12-01: 26; 2021-01-01: 27; 2021-02-01: 28; 2021-03-01: 29; 2021-04-01: 30; 2021-05-01: 31; 2021-06-01: 32; 2021-07-01: 33; 2021-08-01: 34; 2021-09-01: 35; 2021-10-01: 36; 2021-11-01: 37; 2021-12-01: 38; 2022-01-01: 39; 2022-02-01: 40; 2022-03-01: 41; 2022-04-01: 42; 2022-05-01: 43; 2022-06-01: 44; 2022-07-01: 45; 2022-08-01: 46; 2022-09-01: 47; 2022-10-01: 48; 2022-11-01: 49; 2022-12-01: 50; 2023-01-01: 51; 2023-02-01: 52
tfabDC | Days to fabricate 3 set of DC | 10 | 1 | 1 | (WBS 1.5) | [ name ] | [11 empty] | - | - | - | - | - | - |  |  | I12<>"",J12<>"",K12<>"",L12<>""
tfabMUX | Days to fabricate/screen/ship resonators for 2 MMBs | 14 | 2 | 1.1 | Readout PRR | [6 empty] | 2019-04-30 |  | 1 |  |  |  | 2019-04-30 | 2019-04-30 | 1 | 1 | 0 | 1
tfabRF | Days to fabricate RF/RF cap for 3 MMB | 10 | 2 | 1.2 | NIST fab 3 sets of MMBs | [6 empty] | 2019-05-01 | 2019-05-15 | 10 |  |  |  | 2019-05-01 | 2019-05-15
tbondMMB | Days to bond 1 MMB | 3 | 3 | 1.2.1 | Fabrication 3 sets DC(A1-A3) |  |  | 1.1 | [5 empty] | 10 |  |  |  | 2019-05-01 | 2019-05-15
tassMMB | Days to assemble 6 sets MMBs | 34 | 3 | 1.2.2 | Fabrication/screen/ship 2 sets resonators(A1-A2) |  |  | 1.1 | [5 empty] | 14 |  |  |  | 2019-05-01 | 2019-05-21
tvalMMB | Days to test 3 MMBs | 15 | 3 | 1.2.3 | Fabrication/screen/ship 2 sets resonators(A3-B1) |  |  | 1.2.2 | [5 empty] | 14 |  |  |  | 2019-05-22 | 2019-06-11
NISTbatch | NIST batch size | 4 | 3 | 1.2.4 | Fabrication 3 sets RF/cap (A1-A3) |  |  | 1.1 | [5 empty] | 10 |  |  |  | 2019-05-01 | 2019-05-15
tfabNIST | Days to fabricate NIST batch | 30 | 2 | 1.3 | Screen DC wafers (A1-A3) in DR3 |  |  | 1.1 | [5 empty] | 15 |  |  | o | 2019-05-01 | 2019-05-22
tassNIST | Days to assemble NIST UFM | 6 | 2 | 1.4 | Assemble 3 MMBs (A1-A3) | Lbonder |  | 1.2.4 | 1.3 | 1.2.2 |  |  |  | 19 |  |  | k | 2019-05-23 | 2019-06-19
UCBbatch | UCB batch size | 6 | 2 | 1.5 | Test 3 MMBs (A1-A3) in DR1 |  | 3 MMBs | 1.4 | [5 empty] | 15 |  |  | p | 2019-06-20 | 2019-07-11
tfabUCB | Days to fabrication UCB batch | 50 | 2 | 1.6 | NIST fab 6 sets of MMBs | [6 empty] | 2019-05-16 | 2019-06-13 | 10 |  |  |  | 2019-05-16 | 2019-06-13
tassUCB | Days to assemble UCB UFM | 7 | 3 | 1.6.1 | Fabrication 3 sets DC(B1-B3) |  |  | 1.2.1 | [5 empty] | 10 |  |  |  | 2019-05-16 | 2019-05-30
tvalUFM | Days to test 3 UFMs | 30 | 3 | 1.6.2 | Fabrication/screen/ship 2 sets resonators(B2-B3) |  |  | 1.2.3 | [5 empty] | 14 |  |  |  | 2019-06-12 | 2019-07-01
tassSP | Days to assmble single pix | 3 | 3 | 1.6.3 | Fabrication/screen/ship 2 sets resonators(B4-B5) |  |  | 1.6.2 | [5 empty] | 14 |  |  |  | 2019-07-02 | 2019-07-22
tvalSP | Days to test single pix | 17 | 3 | 1.6.4 | Fabrication/screen/ship 2 sets resonators(B6-C1) |  |  | 1.6.3 | [5 empty] | 14 |  |  |  | 2019-07-23 | 2019-08-12
tvalOPT | Days for optical test 1 UFM | 30 | 3 | 1.6.5 | Fabrication 3 sets RF/cap (B1-B3) |  |  | 1.2.4 | [5 empty] | 10 |  |  |  | 2019-05-16 | 2019-05-30
tvalDC | Days to screen DC wafers | 10 | 3 | 1.6.6 | Fabrication 3 sets RF/cap (B4-B6) |  |  | 1.6.5 | [5 empty] | 10 |  |  |  | 2019-05-31 | 2019-06-13
tfabLenslet | Days to fabricate 3 sets of lenslet | 40 | 3 | 1.6.7 | Fabrication 3 sets DC(B4-B6) |  |  | 1.6.1 | [5 empty] | 10 |  |  |  | 2019-05-31 | 2019-06-13
tfabHorn | Days to fabricate 3 sets of horn | 30 | 2 | 1.7 | Screen DC wafers (B1-B6) in DR3 |  |  | 1.6.6 | 1.3 |  |  |  |  | 10 |  |  | o | 2019-06-14 | 2019-06-27
|  |  | 2 | 1.8 | Assemble 6 MMBs (B1-B6) | Lbonder |  | 1.7 | 1.6.6 | 1.4 | 1.6.2 |  |  | 34 |  |  | k | 2019-07-02 | 2019-08-20
|  |  | 2 | 1.9 | Test 3 MMBs (B1-B3) in DR3 |  | 6 MMBs | 1.8 | 1.25 |  |  |  |  | 15 |  |  | o | 2019-08-28 | 2019-09-18
|  |  | 2 | 1.10 | Test 3 MMBs (B4-B6) in DR1 |  | 9 MMBs | 1.8 | 1.5 |  |  |  |  | 15 |  |  | p | 2019-08-21 | 2019-09-12
|  |  | 2 | 1.11 | NIST Detector PRR | [6 empty] | 2019-05-13 |  | 1 |  |  |  | 2019-05-13 | 2019-05-13
|  |  | 2 | 1.12 | NIST fabs 3 MF arrays + 1 single pixel |  |  | 1.11 | [5 empty] | 30 |  |  |  | 2019-05-14 | 2019-06-25
|  |  | 2 | 1.13 | Assemble single pixels | Sbonder |  | 1.12 | [5 empty] | 3 |  |  | 5 | 2019-06-26 | 2019-06-28
|  |  | 2 | 1.14 | Test single pixels in DR4 |  |  | 1.13 | [5 empty] | 17 |  |  | 6 | 2019-07-01 | 2019-07-24
|  |  | 2 | 1.15 | 3 MF horns fab/shipped to Princeton | [6 empty] | 2019-05-14 |  | 30 |  |  | 4 | 2019-05-14 | 2019-06-25
|  |  | 2 | 1.16 | Assemble 3 MF-h UFMs with A1-A3 | Sbonder |  | 1.12 | 1.13 | 1.15 |  |  |  | 6 |  |  | 5 | 2019-07-01 | 2019-07-09
|  |  | 2 | 1.17 | Test 3 MF-h UFMs in DR2 |  | 3 MF-h | 1.16 | [5 empty] | 30 |  |  | g | 2019-07-10 | 2019-08-21
|  |  | 2 | 1.18 | Test 1 of the above MF-h UFM @ UCSD |  |  | 1.17 | [5 empty] | 30 |  |  | r | 2019-08-22 | 2019-10-04
|  |  | 2 | 1.19 | NIST fab 6 sets of MMBs | [6 empty] | 2019-06-14 | 2019-07-12 | 10 |  |  |  | 2019-06-14 | 2019-07-12
|  |  | 3 | 1.19.1 | Fabrication 3 sets DC(C1-C3) |  |  | 1.6.7 | [5 empty] | 10 |  |  |  | 2019-06-14 | 2019-06-27
|  |  | 3 | 1.19.2 | Fabrication/screen/ship 2 sets resonators(C2-C3) |  |  | 1.6.4 | [5 empty] | 14 |  |  |  | 2019-08-13 | 2019-09-03
|  |  | 3 | 1.19.3 | Fabrication/screen/ship 2 sets resonators(C4-C5) |  |  | 1.19.2 | [5 empty] | 14 |  |  |  | 2019-09-04 | 2019-09-23
|  |  | 3 | 1.19.4 | Fabrication/screen/ship 2 sets resonators(C6-D1) |  |  | 1.19.3 | [5 empty] | 14 |  |  |  | 2019-09-24 | 2019-10-11
|  |  | 3 | 1.19.5 | Fabrication 3 sets RF/cap (C1-C3) |  |  | 1.6.6 | [5 empty] | 10 |  |  |  | 2019-06-14 | 2019-06-27
|  |  | 3 | 1.19.6 | Fabrication 3 sets RF/cap (C4-C6) |  |  | 1.19.5 | [5 empty] | 10 |  |  |  | 2019-06-28 | 2019-07-12
|  |  | 3 | 1.19.7 | Fabrication 3 sets DC(C4-C6) |  |  | 1.19.1 | [5 empty] | 10 |  |  |  | 2019-06-28 | 2019-07-12
|  |  | 2 | 1.20 | Screen DC wafers (C1-C6) in DR3 |  |  | 1.19.7 | 1.19.1 | 1.7 |  |  |  | 10 |  |  | o | 2019-07-15 | 2019-07-26
|  |  | 2 | 1.21 | Assemble 6 MMBs (C1-C6) | Lbonder |  | 1.20 | 1.8 | 1.19.2 | 1.19.6 |  |  | 34 |  |  | k | 2019-09-04 | 2019-10-22
|  |  | 2 | 1.22 | Test 3 MMBs (C1-C3) in DR1 |  | 12 MMBs | 1.21 | 1.10 |  |  |  |  | 15 |  |  | p | 2019-10-23 | 2019-11-13
|  |  | 2 | 1.23 | Test 3 MMBs (C4-C6) in DR3 |  | 15 MMBs | 1.21 | 1.9 | 1.51 |  |  |  | 15 |  |  | o | 2019-10-25 | 2019-11-15
|  |  | 2 | 1.24 | NIST fab 6 sets of MMBs | [6 empty] | 2019-07-15 | 2019-08-12 | 10 |  |  |  | 2019-07-15 | 2019-08-12
|  |  | 3 | 1.24.1 | Fabrication 3 sets DC(D1-D3) |  |  | 1.19.7 | [5 empty] | 10 |  |  |  | 2019-07-15 | 2019-07-26
|  |  | 3 | 1.24.2 | Fabrication/screen/ship 2 sets resonators(D2-D3) |  |  | 1.19.4 | [5 empty] | 14 |  |  |  | 2019-10-15 | 2019-11-01
|  |  | 3 | 1.24.3 | Fabrication/screen/ship 2 sets resonators(D4-D5) |  |  | 1.24.2 | [5 empty] | 14 |  |  |  | 2019-11-04 | 2019-11-22
|  |  | 3 | 1.24.4 | Fabrication/screen/ship 2 sets resonators(D6-E1) |  |  | 1.24.3 | [5 empty] | 14 |  |  |  | 2019-11-25 | 2019-12-13
|  |  | 3 | 1.24.5 | Fabrication 3 sets RF/cap (D1-D3) |  |  | 1.19.6 | [5 empty] | 10 |  |  |  | 2019-07-15 | 2019-07-26
|  |  | 3 | 1.24.6 | Fabrication 3 sets RF/cap (D4-D6) |  |  | 1.24.5 | [5 empty] | 10 |  |  |  | 2019-07-29 | 2019-08-12
|  |  | 3 | 1.24.7 | Fabrication 3 sets DC(D4-D6) |  |  | 1.24.1 | [5 empty] | 10 |  |  |  | 2019-07-29 | 2019-08-12
|  |  | 2 | 1.25 | Screen DC wafers (D1-D6) in DR3 |  |  | 1.24.7 | 1.24.1 | 1.20 |  |  |  | 10 |  |  | o | 2019-08-13 | 2019-08-27
|  |  | 2 | 1.26 | Assemble 6 MMBs (D1-D6) | Lbonder |  | 1.21 | 1.25 | 1.24.6 | 1.24.2 |  |  | 34 |  |  | k | 2019-11-04 | 2019-12-23
|  |  | 2 | 1.27 | Test 3 MMBs (D1-D3) in DR1 |  | 18 MMBs | 1.26 | 1.44 |  |  |  |  | 15 |  |  | p | 2020-01-10 | 2020-01-31
|  |  | 2 | 1.28 | Test 3 MMBs (D4-D6) in DR3 |  | 21 MMBs | 1.26 | 1.65 |  |  |  |  | 15 |  |  | o | 2019-12-24 | 2020-01-16
|  |  | 2 | 1.29 | NIST fab 6 sets of MMBs | [6 empty] | 2019-08-13 | 2019-09-11 | 10 |  |  |  | 2019-08-13 | 2019-09-11
|  |  | 3 | 1.29.1 | Fabrication 3 sets DC(E1-E3) |  |  | 1.24.7 | [5 empty] | 10 |  |  |  | 2019-08-13 | 2019-08-27
|  |  | 3 | 1.29.2 | Fabrication/screen/ship 2 sets resonators(E2-E3) |  |  | 1.24.4 | [5 empty] | 14 |  |  |  | 2019-12-16 | 2020-01-07
|  |  | 3 | 1.29.3 | Fabrication/screen/ship 2 sets resonators(E4-E5) |  |  | 1.29.2 | [5 empty] | 14 |  |  |  | 2020-01-08 | 2020-01-28
|  |  | 3 | 1.29.4 | Fabrication/screen/ship 2 sets resonators(E6-F1) |  |  | 1.29.3 | [5 empty] | 14 |  |  |  | 2020-01-29 | 2020-02-18
|  |  | 3 | 1.29.5 | Fabrication 3 sets RF/cap (E1-E3) |  |  | 1.24.6 | [5 empty] | 10 |  |  |  | 2019-08-13 | 2019-08-27
|  |  | 3 | 1.29.6 | Fabrication 3 sets RF/cap (E4-E6) |  |  | 1.29.5 | [5 empty] | 10 |  |  |  | 2019-08-28 | 2019-09-11
|  |  | 3 | 1.29.7 | Fabrication 3 sets DC(E4-E6) |  |  | 1.29.1 | [5 empty] | 10 |  |  |  | 2019-08-28 | 2019-09-11
|  |  | 2 | 1.30 | Screen DC wafers (E1-E6) in DR3 |  |  | 1.29.7 | 1.29.1 |  |  | 2019-08-28 | 2019-09-18 | 10 |  |  | o | 2019-08-28 | 2019-09-18
|  |  | 2 | 1.31 | Assemble 6 MMBs (E1-E6) | Lbonder |  | 1.26 | 1.30 | 1.29.6 | 1.29.2 |  |  | 34 |  |  | k | 2020-01-08 | 2020-02-26
|  |  | 2 | 1.32 | Test 3 MMBs (E1-E3) in DR1 |  | 24 MMBs | 1.31 | 1.27 |  |  |  |  | 15 |  |  | p | 2020-02-27 | 2020-03-18
|  |  | 2 | 1.33 | Test 3 MMBs (E4-E6) in DR3 |  | 27 MMBs | 1.31 | 1.89 |  |  |  |  | 15 |  |  | o | 2020-02-27 | 2020-03-18
|  |  | 2 | 1.34 | NIST fabs 3 arrays |  |  | 1.12 | [5 empty] | 30 |  |  |  | 2019-06-26 | 2019-08-08
|  |  | 2 | 1.35 | 3 MF horns fab/shipped to Princeton |  |  | 1.15 | [5 empty] | 30 |  |  | 4 | 2019-06-26 | 2019-08-08
|  |  | 2 | 1.36 | Assemble 3 UFM-hs w/ B1-B3 | Sbonder |  | 1.34 | 1.16 | 1.13 | 1.35 |  |  | 6 |  |  | 5 | 2019-08-09 | 2019-08-16
|  |  | 2 | 1.37 | Test 3 UFMs in DR2 |  | 6 MF-h | 1.36 | 1.17 |  |  |  |  | 30 |  |  | g | 2019-08-22 | 2019-10-04
|  |  | 2 | 1.38 | UCB Detector PRR | [6 empty] | 2019-06-06 |  | 1 |  |  |  | 2019-06-06 | 2019-06-06
|  |  | 2 | 1.39 | UCB fabs 6 arrays + 1 single pixel |  |  | 1.38 | [5 empty] | 50 |  |  | 2 | 2019-06-07 | 2019-08-19
|  |  | 2 | 1.40 | 3 sets of lenslet wafers fabricated |  |  | 1.38 | [5 empty] | 40 |  |  | 1 | 2019-06-07 | 2019-08-02
|  |  | 2 | 1.41 | Assemble single pixels | Sbonder |  | 1.39 | 1.36 |  |  |  |  | 3 |  |  | 5 | 2019-08-20 | 2019-08-22
|  |  | 2 | 1.42 | Test single pixels in DR4 |  |  | 1.41 | 1.14 |  |  |  |  | 17 |  |  | 6 | 2019-08-23 | 2019-09-18
|  |  | 2 | 1.43 | Assemble 3 UCB UFMs w/ C1-C3 | Bbonder |  | 1.39 | 1.22 | 1.40 |  |  |  | 7 |  |  | 3 | 2019-11-14 | 2019-11-22
|  |  | 2 | 1.44 | Test 3 UFMs in DR1 |  | 3 MF-l | 1.43 | 1.22 |  |  |  |  | 30 |  |  | p | 2019-11-25 | 2020-01-09
|  |  | 2 | 1.45 | Test 1 of the above 3 UFM @ UCSD |  |  | 1.44 | 1.18 |  |  |  |  | 30 |  |  | r | 2020-01-10 | 2020-02-24
|  |  | 2 | 1.46 | 3 sets of lenslet wafers fabricated |  |  | 1.40 | [5 empty] | 40 |  |  | 2 | 2019-08-06 | 2019-10-02
|  |  | 2 | 1.47 | Assemble 3 UCB UFMs w/ C4-C6 | Bbonder |  | 1.43 | 1.23 | 1.39 | 1.46 |  |  | 7 |  |  | 3 | 2019-11-25 | 2019-12-04
|  |  | 2 | 1.48 | Test 3 UFMs in DR2 | LATR1 | 6 MF-l | 1.47 | 1.63 |  |  |  |  | 30 |  |  | g | 2019-12-05 | 2020-01-21
|  |  | 2 | 1.49 | Test 1 of the above 3 UFM @ UCSD |  |  | 1.45 | 1.48 |  |  |  |  | 30 |  |  | r | 2020-02-25 | 2020-04-06
|  |  | 2 | 1.50 | NIST fab 6 sets of MMBs | [6 empty] | 2019-09-12 | 2019-10-09 | 10 |  |  |  | 2019-09-12 | 2019-10-09
|  |  | 3 | 1.50.1 | Fabrication 3 sets DC(F1-F3) |  |  | 1.29.7 | [5 empty] | 10 |  |  |  | 2019-09-12 | 2019-09-25
|  |  | 3 | 1.50.2 | Fabrication/screen/ship 2 sets resonators(F2-F3) |  |  | 1.29.2 | [5 empty] | 14 |  |  |  | 2020-01-08 | 2020-01-28
|  |  | 3 | 1.50.3 | Fabrication/screen/ship 2 sets resonators(F4-F5) |  |  | 1.50.2 | [5 empty] | 14 |  |  |  | 2020-01-29 | 2020-02-18
|  |  | 3 | 1.50.4 | Fabrication/screen/ship 2 sets resonators(F6-G1) |  |  | 1.50.3 | [5 empty] | 14 |  |  |  | 2020-02-19 | 2020-03-09
|  |  | 3 | 1.50.5 | Fabrication 3 sets RF/cap (F1-F3) |  |  | 1.29.6 | [5 empty] | 10 |  |  |  | 2019-09-12 | 2019-09-25
|  |  | 3 | 1.50.6 | Fabrication 3 sets RF/cap (F4-F6) |  |  | 1.50.5 | [5 empty] | 10 |  |  |  | 2019-09-26 | 2019-10-09
|  |  | 3 | 1.50.7 | Fabrication 3 sets DC(F4-F6) |  |  | 1.50.1 | [5 empty] | 10 |  |  |  | 2019-09-26 | 2019-10-09
|  |  | 2 | 1.51 | Screen DC wafers (F1-F6) in DR3 |  |  | 1.50.7 | 1.50.1 | 1.30 |  |  |  | 10 |  |  | o | 2019-10-10 | 2019-10-24
|  |  | 2 | 1.52 | Assemble 6 MMBs (F1-F6) | Lbonder |  | 1.31 | 1.51 | 1.50.6 | 1.50.2 |  |  | 34 |  |  | k | 2020-02-27 | 2020-04-16
|  |  | 2 | 1.53 | Test 3 MMBs (F1-F3) in DR1 |  | 30 MMBs | 1.52 | 1.32 |  |  |  |  | 15 |  |  | p | 2020-04-17 | 2020-05-08
|  |  | 2 | 1.54 | Test 3 MMBs (F4-F6) in DR1 |  | 33 MMBs | 1.52 | 1.96 |  |  |  |  | 15 |  |  | p | 2020-05-21 | 2020-06-11
|  |  | 2 | 1.55 | NIST fab 6 sets of MMBs | [6 empty] | 2019-10-10 | 2019-11-07 | 10 |  |  |  | 2019-10-10 | 2019-11-07
|  |  | 3 | 1.55.1 | Fabrication 3 sets DC(G1-G3) |  |  | 1.50.7 | [5 empty] | 10 |  |  |  | 2019-10-10 | 2019-10-24
|  |  | 3 | 1.55.2 | Fabrication/screen/ship 2 sets resonators(G2-G3) |  |  | 1.50.4 | [5 empty] | 14 |  |  |  | 2020-03-10 | 2020-03-27
|  |  | 3 | 1.55.3 | Fabrication/screen/ship 2 sets resonators(G4-G5) |  |  | 1.55.2 | [5 empty] | 14 |  |  |  | 2020-03-30 | 2020-04-20
|  |  | 3 | 1.55.4 | Fabrication/screen/ship 2 sets resonators(G6-H1) |  |  | 1.55.3 | [5 empty] | 14 |  |  |  | 2020-04-21 | 2020-05-11
|  |  | 3 | 1.55.5 | Fabrication 3 sets RF/cap (G1-G3) |  |  | 1.50.6 | [5 empty] | 10 |  |  |  | 2019-10-10 | 2019-10-24
|  |  | 3 | 1.55.6 | Fabrication 3 sets RF/cap (G4-G6) |  |  | 1.55.5 | [5 empty] | 10 |  |  |  | 2019-10-25 | 2019-11-07
|  |  | 3 | 1.55.7 | Fabrication 3 sets DC(G4-G6) |  |  | 1.55.1 | [5 empty] | 10 |  |  |  | 2019-10-25 | 2019-11-07
|  |  | 2 | 1.56 | Screen DC wafers (G1-G6) in DR3 |  |  | 1.55.7 | 1.55.1 | 1.23 |  |  |  | 10 |  |  | o | 2019-11-18 | 2019-12-02
|  |  | 2 | 1.57 | Assemble 6 MMBs (G1-G6) | Lbonder |  | 1.52 | 1.56 | 1.55.6 |  | 2020-03-27 |  | 34 |  |  | k | 2020-03-27 | 2020-05-18
|  |  | 2 | 1.58 | Test 3 MMBs (G1-G3) in DR3 |  | 36 MMBs | 1.57 |  | 1.84 |  |  |  | 15 |  |  | o | 2020-05-19 | 2020-06-09
|  |  | 2 | 1.59 | Test 3 MMBs (G4-G6) in DR3 |  | 39 MMBs | 1.57 |  | 1.58 |  |  |  | 15 |  |  | o | 2020-06-10 | 2020-06-30
|  |  | 2 | 1.60 | NIST fabs 3 arrays |  |  | 1.34 | [5 empty] | 30 |  |  |  | 2019-08-09 | 2019-09-23
|  |  | 2 | 1.61 | 3 MF horns fab/shipped to Princeton |  |  | 1.35 | [5 empty] | 30 |  |  | 4 | 2019-08-09 | 2019-09-23
|  |  | 2 | 1.62 | Assemble 3 UFMs w/ B4-B6 | Sbonder |  | 1.60 | 1.10 | 1.41 | 1.61 |  |  | 6 |  |  | 5 | 2019-09-24 | 2019-10-01
|  |  | 2 | 1.63 | Test 3 UFMs in DR2 | SAT1 | 9 MF-h | 1.62 | 1.37 |  |  |  |  | 30 |  |  | g | 2019-10-07 | 2019-11-19
|  |  | 2 | 1.64 | NIST fab 6 sets of MMBs | [6 empty] | 2019-11-08 | 2019-12-09 | 10 |  |  |  | 2019-11-08 | 2019-12-09
|  |  | 3 | 1.64.1 | Fabrication 3 sets DC(H1-H3) |  |  | 1.55.7 | [5 empty] | 10 |  |  |  | 2019-11-08 | 2019-11-22
|  |  | 3 | 1.64.2 | Fabrication/screen/ship 2 sets resonators(H2-H3) |  |  | 1.55.4 | [5 empty] | 14 |  |  |  | 2020-05-12 | 2020-06-01
|  |  | 3 | 1.64.3 | Fabrication/screen/ship 2 sets resonators(H4-H5) |  |  | 1.64.2 | [5 empty] | 14 |  |  |  | 2020-06-02 | 2020-06-19
|  |  | 3 | 1.64.4 | Fabrication/screen/ship 2 sets resonators(H6-I1) |  |  | 1.64.3 | [5 empty] | 14 |  |  |  | 2020-06-22 | 2020-07-09
|  |  | 3 | 1.64.5 | Fabrication 3 sets RF/cap (H1-H3) |  |  | 1.55.6 | [5 empty] | 10 |  |  |  | 2019-11-08 | 2019-11-22
|  |  | 3 | 1.64.6 | Fabrication 3 sets RF/cap (H4-H6) |  |  | 1.64.5 | [5 empty] | 10 |  |  |  | 2019-11-25 | 2019-12-09
|  |  | 3 | 1.64.7 | Fabrication 3 sets DC(H4-H6) |  |  | 1.64.1 | [5 empty] | 10 |  |  |  | 2019-11-25 | 2019-12-09
|  |  | 2 | 1.65 | Screen DC wafers (H1-H6) in DR3 |  |  | 1.64.7 | 1.64.1 | 1.56 |  |  |  | 10 |  |  | o | 2019-12-10 | 2019-12-23
|  |  | 2 | 1.66 | Assemble 6 MMBs (H1-H6) | Lbonder |  | 1.57 | 1.65 | 1.64.6 |  | 2020-06-01 |  | 34 |  |  | k | 2020-06-01 | 2020-07-16
|  |  | 2 | 1.67 | Test 3 MMBs (H1-H3) in DR1 |  | 42 MMBs | 1.66 | 1.58 |  |  |  |  | 15 |  |  | p | 2020-07-17 | 2020-08-07
|  |  | 2 | 1.68 | Test 3 MMBs (H4-H6) in DR1 |  | 45 MMBs | 1.66 | 1.67 |  |  |  |  | 15 |  |  | p | 2020-08-10 | 2020-08-28
|  |  | 2 | 1.69 | UCB fabs 6 arrays |  |  | 1.39 | [5 empty] | 50 |  |  | 2 | 2019-08-20 | 2019-10-31
|  |  | 2 | 1.70 | 3 sets of lenslet wafers fabricated |  |  | 1.46 | [5 empty] | 40 |  |  | 1 | 2019-10-03 | 2019-12-02
|  |  | 2 | 1.71 | Assemble 3 UCB UFMs w/ D1-D3 | Bbonder |  | 1.69 | 1.27 | 1.47 | 1.70 |  |  | 7 |  |  | 3 | 2020-02-03 | 2020-02-11
|  |  | 2 | 1.72 | Test 3 UFMs in DR2 | LATR2 | 9 MF-l | 1.71 | 1.48 |  |  |  |  | 30 |  |  | g | 2020-02-12 | 2020-03-25
|  |  | 2 | 1.73 | 3 sets of lenslet wafers fabricated |  |  | 1.70 | [5 empty] | 40 |  |  | 1 | 2019-12-03 | 2020-01-31
|  |  | 2 | 1.74 | Assemble 3 UCB UFMs w/ D4-D6 | Bbonder |  | 1.71 | 1.28 | 1.69 | 1.73 |  |  | 7 |  |  | 3 | 2020-02-12 | 2020-02-21
|  |  | 2 | 1.75 | Test 3 UFMs in DR2 |  | 12 MF-l | 1.74 | 1.72 |  |  |  |  | 30 |  |  | g | 2020-03-26 | 2020-05-11
|  |  | 2 | 1.76 | NIST fabs 3 UHF arrays + 1 single pixel |  |  | 1.60 | [5 empty] | 30 |  |  |  | 2019-09-24 | 2019-11-05
|  |  | 2 | 1.77 | Assemble single pixels | Sbonder |  | 1.76 | 1.62 |  |  |  |  | 3 |  |  | 5 | 2019-11-06 | 2019-11-08
|  |  | 2 | 1.78 | test single pixels In DR4 |  |  | 1.77 | 1.42 |  |  |  |  | 17 |  |  | 6 | 2019-11-12 | 2019-12-05
|  |  | 2 | 1.79 | 3 MF horns fab/shipped to Princeton |  |  | 1.61 | [5 empty] | 30 |  |  | 4 | 2019-09-24 | 2019-11-05
|  |  | 2 | 1.80 | Assemble 3 UFMs w/ E1-E3 | Sbonder |  | 1.32 | 1.76 | 1.77 | 1.79 |  |  | 6 |  |  | 5 | 2020-03-19 | 2020-03-26
|  |  | 2 | 1.81 | Test 3 UFMs in DR3 |  | 3 UHF-h | 1.33 | 1.122 |  |  |  |  | 30 |  |  | o | 2020-10-02 | 2020-11-16
|  |  | 2 | 1.82 | Test 1 of the above 3 UFM @ UCSD |  |  | 1.81 | 1.49 |  |  |  |  | 30 |  |  | r | 2020-11-17 | 2020-12-30
|  |  | 2 | 1.83 | NIST fab 6 sets of MMBs | [6 empty] | 2019-12-10 | 2020-01-09 | 10 |  |  |  | 2019-12-10 | 2020-01-09
|  |  | 3 | 1.83.1 | Fabrication 3 sets DC(I1-I3) |  |  | 1.64.7 | [5 empty] | 10 |  |  |  | 2019-12-10 | 2019-12-23
|  |  | 3 | 1.83.2 | Fabrication/screen/ship 2 sets resonators(I2-I3) |  |  | 1.64.4 | [5 empty] | 14 |  |  |  | 2020-07-10 | 2020-07-29
|  |  | 3 | 1.83.3 | Fabrication/screen/ship 2 sets resonators(I4-I5) |  |  | 1.83.2 | [5 empty] | 14 |  |  |  | 2020-07-30 | 2020-08-19
|  |  | 3 | 1.83.4 | Fabrication/screen/ship 2 sets resonators(I6-J1) |  |  | 1.83.3 | [5 empty] | 14 |  |  |  | 2020-08-20 | 2020-09-10
|  |  | 3 | 1.83.5 | Fabrication 3 sets RF/cap (I1-I3) |  |  | 1.64.6 | [5 empty] | 10 |  |  |  | 2019-12-10 | 2019-12-23
|  |  | 3 | 1.83.6 | Fabrication 3 sets RF/cap (I4-I6) |  |  | 1.83.5 | [5 empty] | 10 |  |  |  | 2019-12-24 | 2020-01-09
|  |  | 3 | 1.83.7 | Fabrication 3 sets DC(I4-I6) |  |  | 1.83.1 | [5 empty] | 10 |  |  |  | 2019-12-24 | 2020-01-09
|  |  | 2 | 1.84 | Screen DC wafers (I1-I6) in DR3 |  |  | 1.83.7 | 1.83.1 | 1.28 |  |  |  | 10 |  |  | o | 2020-01-17 | 2020-01-31
|  |  | 2 | 1.85 | Assemble 6 MMBs (I1-I6) | Lbonder |  | 1.66 | 1.84 | 1.83.6 |  | 2020-07-29 |  | 34 |  |  | k | 2020-07-29 | 2020-09-17
|  |  | 2 | 1.86 | Test 3 MMBs (I1-I3) in DR1 |  | 48 MMBs | 1.85 | 1.68 |  |  |  |  | 15 |  |  | p | 2020-09-18 | 2020-10-08
|  |  | 2 | 1.87 | Test 3 MMBs (I4-I6) in DR1 |  | 51 MMBs | 1.85 | 1.86 |  |  |  |  | 15 |  |  | p | 2020-10-09 | 2020-10-30
|  |  | 2 | 1.88 | NIST fab 6 sets of MMBs | [6 empty] | 2020-01-10 | 2020-02-07 | 10 |  |  |  | 2020-01-10 | 2020-02-07
|  |  | 3 | 1.88.1 | Fabrication 3 sets DC(J1-J3) |  |  | 1.83.7 | [5 empty] | 10 |  |  |  | 2020-01-10 | 2020-01-24
|  |  | 3 | 1.88.2 | Fabrication/screen/ship 2 sets resonators(J2-J3) |  |  | 1.83.4 | [5 empty] | 14 |  |  |  | 2020-09-11 | 2020-09-30
|  |  | 3 | 1.88.3 | Fabrication/screen/ship 2 sets resonators(J4-J5) |  |  | 1.88.2 | [5 empty] | 14 |  |  |  | 2020-10-01 | 2020-10-21
|  |  | 3 | 1.88.4 | Fabrication/screen/ship 2 sets resonators(J6-K1) |  |  | 1.88.3 | [5 empty] | 14 |  |  |  | 2020-10-22 | 2020-11-10
|  |  | 3 | 1.88.5 | Fabrication 3 sets RF/cap (J1-J3) |  |  | 1.83.5 | [5 empty] | 10 |  |  |  | 2019-12-24 | 2020-01-09
|  |  | 3 | 1.88.6 | Fabrication 3 sets RF/cap (J4-J6) |  |  | 1.88.5 | [5 empty] | 10 |  |  |  | 2020-01-10 | 2020-01-24
|  |  | 3 | 1.88.7 | Fabrication 3 sets DC(J4-J6) |  |  | 1.88.1 | [5 empty] | 10 |  |  |  | 2020-01-27 | 2020-02-07
|  |  | 2 | 1.89 | Screen DC wafers (J1-J6) in DR3 |  |  | 1.88.7 | 1.88.1 | 1.84 |  |  |  | 10 |  |  | o | 2020-02-10 | 2020-02-24
|  |  | 2 | 1.90 | Assemble 6 MMBs (J1-J6) | Lbonder |  | 1.85 | 1.89 | 1.88.6 |  | 2020-09-30 |  | 34 |  |  | k | 2020-09-30 | 2020-11-18
|  |  | 2 | 1.91 | Test 3 MMBs (J1-J3) in DR1 |  | 54 MMBs | 1.90 | 1.87 |  |  |  |  | 15 |  |  | p | 2020-11-19 | 2020-12-10
|  |  | 2 | 1.92 | Test 3 MMBs (J4-J6) in DR1 |  | 57 MMBs | 1.90 | 1.91 |  |  |  |  | 15 |  |  | p | 2020-12-11 | 2021-01-04
|  |  | 2 | 1.93 | NIST fabs 3 arrays |  |  | 1.76 | [5 empty] | 30 |  |  |  | 2019-11-06 | 2019-12-19
|  |  | 2 | 1.94 | 3 MF horns fab/shipped to Princeton |  |  | 1.79 | [5 empty] | 30 |  |  | 4 | 2019-11-06 | 2019-12-19
|  |  | 2 | 1.95 | Assemble 3 UFMs w/ E4-E6 | Sbonder |  | 1.93 | 1.80 | 1.94 | 1.33 |  |  | 6 |  |  | 5 | 2020-03-27 | 2020-04-03
|  |  | 2 | 1.96 | Test 3 UFMs in DR1 | LATR3 | 6 UHF-h | 1.95 | 1.32 |  |  |  |  | 30 |  |  | p | 2020-04-06 | 2020-05-20
|  |  | 2 | 1.97 | UCB fabs 6 arrays |  |  | 1.69 | [5 empty] | 50 |  |  | 2 | 2019-11-01 | 2020-01-16
|  |  | 2 | 1.98 | 3 sets of lenslet wafers fabricated |  |  | 1.73 | [5 empty] | 40 |  |  | 1 | 2020-02-03 | 2020-03-30
|  |  | 2 | 1.99 | Assemble 3 UCB UFMs w/ F1-F3 | Bbonder |  | 1.97 | 1.74 | 1.53 | 1.98 |  |  | 7 |  |  | 3 | 2020-05-11 | 2020-05-19
|  |  | 2 | 1.100 | Test 3 UFMs in DR3 | LATR4 | 15 MF-l | 1.99 | 1.33 |  |  |  |  | 30 |  |  | o | 2020-05-20 | 2020-07-01
|  |  | 2 | 1.101 | 3 sets of lenslet wafers fabricated |  |  | 1.98 | [5 empty] | 40 |  |  | 1 | 2020-03-31 | 2020-05-29
|  |  | 2 | 1.102 | Assemble 3 UCB UFMs w/ F4-F6 | Bbonder |  | 1.99 | 1.97 | 1.54 | 1.101 |  |  | 7 |  |  | 3 | 2020-06-12 | 2020-06-22
|  |  | 2 | 1.103 | Test 3 UFMs in DR3 | LATR5 | 18 MF-l | 1.102 | 1.58 |  |  |  |  | 30 |  |  | o | 2020-06-23 | 2020-08-04
|  |  | 2 | 1.104 | NIST fab 6 sets of MMBs | [6 empty] | 2020-02-10 | 2020-03-09 | 10 |  |  |  | 2020-02-10 | 2020-03-09
|  |  | 3 | 1.104.1 | Fabrication 3 sets DC(K1-K3) |  |  | 1.88.7 | [5 empty] | 10 |  |  |  | 2020-02-10 | 2020-02-24
|  |  | 3 | 1.104.2 | Fabrication/screen/ship 2 sets resonators(K2-K3) |  |  | 1.88.2 | [5 empty] | 14 |  |  |  | 2020-10-01 | 2020-10-21
|  |  | 3 | 1.104.3 | Fabrication/screen/ship 2 sets resonators(K4-K5) |  |  | 1.104.2 | [5 empty] | 14 |  |  |  | 2020-10-22 | 2020-11-10
|  |  | 3 | 1.104.4 | Fabrication/screen/ship 2 sets resonators(K6-K1) |  |  | 1.104.3 | [5 empty] | 14 |  |  |  | 2020-11-12 | 2020-12-02
|  |  | 3 | 1.104.5 | Fabrication 3 sets RF/cap (K1-K3) |  |  | 1.88.6 | [5 empty] | 10 |  |  |  | 2020-01-27 | 2020-02-07
|  |  | 3 | 1.104.6 | Fabrication 3 sets RF/cap (K4-K6) |  |  | 1.104.5 | [5 empty] | 10 |  |  |  | 2020-02-10 | 2020-02-24
|  |  | 3 | 1.104.7 | Fabrication 3 sets DC(K4-K6) |  |  | 1.104.1 | [5 empty] | 10 |  |  |  | 2020-02-25 | 2020-03-09
|  |  | 2 | 1.105 | Screen DC wafers (K1-K6) in DR3 |  |  | 1.104.7 | 1.104.1 | 1.122 |  | 2020-10-02 | 2020-11-16 | 10 |  |  | o | 2020-10-02 | 2020-11-16
|  |  | 2 | 1.106 | Assemble 6 MMBs (K1-K6) | Lbonder |  | 1.90 | 1.105 | 1.104.6 |  | 2020-10-21 |  | 34 |  |  | k | 2020-10-21 | 2020-12-09
|  |  | 2 | 1.107 | Test 3 MMBs (K1-K3) in DR1 |  | 60 MMBs | 1.106 | 1.92 |  |  |  |  | 15 |  |  | p | 2021-01-05 | 2021-01-26
|  |  | 2 | 1.108 | Test 3 MMBs (K4-K6) in DR3 |  | 63 MMBs | 1.106 | 1.133 |  |  |  |  | 15 |  |  | o | 2021-01-19 | 2021-02-08
|  |  | 2 | 1.109 | NIST fab 6 sets of MMBs | [6 empty] | 2020-03-10 | 2020-04-06 | 10 |  |  |  | 2020-03-10 | 2020-04-06
|  |  | 3 | 1.109.1 | Fabrication 3 sets DC(L1-L3) |  |  | 1.104.7 | [5 empty] | 10 |  |  |  | 2020-03-10 | 2020-03-23
|  |  | 3 | 1.109.2 | Fabrication/screen/ship 2 sets resonators(L2-L3) |  |  | 1.104.4 | [5 empty] | 14 |  |  |  | 2020-12-03 | 2020-12-22
|  |  | 3 | 1.109.3 | Fabrication/screen/ship 2 sets resonators(L4-L5) |  |  | 1.109.2 | [5 empty] | 14 |  |  |  | 2020-12-23 | 2021-01-13
|  |  | 3 | 1.109.4 | Fabrication/screen/ship 2 sets resonators(L6-M1) |  |  | 1.109.3 | [5 empty] | 14 |  |  |  | 2021-01-14 | 2021-02-03
|  |  | 3 | 1.109.5 | Fabrication 3 sets RF/cap (L1-L3) |  |  | 1.104.6 | [5 empty] | 10 |  |  |  | 2020-02-25 | 2020-03-09
|  |  | 3 | 1.109.6 | Fabrication 3 sets RF/cap (L4-L6) |  |  | 1.109.5 | [5 empty] | 10 |  |  |  | 2020-03-10 | 2020-03-23
|  |  | 3 | 1.109.7 | Fabrication 3 sets DC(L4-L6) |  |  | 1.109.1 | [5 empty] | 10 |  |  |  | 2020-03-24 | 2020-04-06
|  |  | 2 | 1.110 | Screen DC wafers (L1-L6) in DR3 |  |  | 1.109.7 | 1.109.1 | 1.105 |  |  |  | 10 |  |  | o | 2020-11-17 | 2020-12-01
|  |  | 2 | 1.111 | Assemble 6 MMBs (L1-L6) | Lbonder |  | 1.106 | 1.110 | 1.109.6 |  | 2020-12-22 |  | 34 |  |  | k | 2020-12-22 | 2021-02-10
|  |  | 2 | 1.112 | Test 3 MMBs (L1-L3) in DR3 |  | 66 MMBs | 1.111 | 1.108 |  |  |  |  | 15 |  |  | o | 2021-02-11 | 2021-03-04
|  |  | 2 | 1.113 | NIST fabs 3 arrays |  |  | 1.93 | [5 empty] | 30 |  |  |  | 2019-12-20 | 2020-02-05
|  |  | 2 | 1.114 | 3 MF horns fab/shipped to Princeton |  |  | 1.94 | [5 empty] | 30 |  |  | 4 | 2019-12-20 | 2020-02-05
|  |  | 2 | 1.115 | Assemble 3 UFMs w/G1-G3 | Sbonder |  | 1.113 | 1.58 | 1.95 | 1.114 |  |  | 6 |  |  | k | 2020-06-10 | 2020-06-17
|  |  | 2 | 1.116 | Test 3 UFMs in DR2 | LATR6 | 9 UHF-h | 1.115 | 1.100 |  |  |  |  | 30 |  |  | g | 2020-07-02 | 2020-08-13
|  |  | 2 | 1.117 | UCB fabs 6 LF arrays & single pixels |  |  | 1.97 | [5 empty] | 50 |  |  | 2 | 2020-01-17 | 2020-03-30
|  |  | 2 | 1.118 | Assemble single pixels | Sbonder |  | 1.117 | 1.115 |  |  |  |  | 3 |  |  | 5 | 2020-06-18 | 2020-06-22
|  |  | 2 | 1.119 | test single pixels UCSD |  |  | 1.118 | 1.82 |  |  |  |  | 17 |  |  | r | 2020-12-31 | 2021-01-26
|  |  | 2 | 1.120 | 3 sets of lenslet wafers fabricated |  |  | 1.101 | [5 empty] | 40 |  |  | 1 | 2020-06-01 | 2020-07-24
|  |  | 2 | 1.121 | Assemble 3 UCB UFMs w/ H1-H3 | Bbonder |  | 1.117 | 1.67 | 1.102 | 1.120 |  |  | 7 |  |  | 3 | 2020-08-10 | 2020-08-18
|  |  | 2 | 1.122 | Test 3 UFMs in DR3 |  | 3 LF-l | 1.121 | 1.103 |  |  |  |  | 30 |  |  | o | 2020-08-19 | 2020-10-01
|  |  | 2 | 1.123 | 3 sets of lenslet wafers fabricated |  |  | 1.120 | [5 empty] | 40 |  |  | 1 | 2020-07-27 | 2020-09-23
|  |  | 2 | 1.124 | Assemble 3 UCB UFMs w/ H4-H6 | Bbonder |  | 1.121 | 1.117 | 1.68 | 1.123 |  |  | 7 |  |  | 3 | 2020-09-24 | 2020-10-02
|  |  | 2 | 1.125 | Test 3 UFMs in DR2 | LATR7 | 6 LF-l | 1.124 | 1.129 |  |  |  |  | 30 |  |  | g | 2020-10-05 | 2020-11-17
|  |  | 2 | 1.126 | NIST fabs 3 arrays |  |  | 1.113 | [5 empty] | 30 |  |  |  | 2020-02-06 | 2020-03-19
|  |  | 2 | 1.127 | 3 MF horns fab/shipped to Princeton |  |  | 1.114 | [5 empty] | 30 |  |  | 4 | 2020-02-06 | 2020-03-19
|  |  | 2 | 1.128 | Assemble 3 UFMs w/G4-G6 | Sbonder |  | 1.126 | 1.59 | 1.118 | 1.127 |  |  | 6 |  |  | 5 | 2020-07-01 | 2020-07-08
|  |  | 2 | 1.129 | Test 3 UFMs in DR2 |  | 12 UFM-h | 1.128 | 1.116 |  |  |  |  | 30 |  |  | g | 2020-08-14 | 2020-09-28
|  |  | 2 | 1.130 | UCB fabs 6 arrays |  |  | 1.117 | [5 empty] | 50 |  |  | 2 | 2020-03-31 | 2020-06-12
|  |  | 2 | 1.131 | 3 sets of lenslet wafers fabricated |  |  | 1.123 | [5 empty] | 40 |  |  | 1 | 2020-09-24 | 2020-11-20
|  |  | 2 | 1.132 | Assemble 3 UCB UFMs w/ I1-I3 | Bbonder |  | 1.130 | 1.124 | 1.86 | 1.131 |  |  | 7 |  |  | 3 | 2020-11-23 | 2020-12-02
|  |  | 2 | 1.133 | Test 3 UFMs in DR3 |  | 9 LF-l | 1.132 | 1.125 |  |  |  |  | 30 |  |  | o | 2020-12-03 | 2021-01-15
|  |  | 2 | 1.134 | 3 sets of lenslet wafers fabricated |  |  | 1.131 | [5 empty] | 40 |  |  | 1 | 2020-11-23 | 2021-01-21
|  |  | 2 | 1.135 | Assemble 3 UCB UFMs w/ I4-I6 | Bbonder |  | 1.132 | 1.132 | 1.87 | 1.134 |  |  | 7 |  |  | 3 | 2021-01-22 | 2021-02-01
|  |  | 2 | 1.136 | Test 3 UFMs in DR1 |  | 12 LF-l | 1.135 | 1.107 |  |  |  |  | 30 |  |  | p | 2021-02-02 | 2021-03-16
|  |  | 2 | 1.137 | NIST fabs 3 arrays |  |  | 1.126 | [5 empty] | 30 |  |  |  | 2020-03-20 | 2020-05-05
|  |  | 2 | 1.138 | 3 MF horns fab/shipped to Princeton |  |  | 1.127 | [5 empty] | 30 |  |  | 4 | 2020-03-20 | 2020-05-05
|  |  | 2 | 1.139 | Assemble 3 UFMs w/ J1-J3 | Lbonder |  | 1.137 | 1.91 | 1.128 | 1.138 |  |  | 6 |  |  | k | 2020-12-11 | 2020-12-18
|  |  | 2 | 1.140 | Test 3 UFMs in DR2 | SAT2 | 15 UHF-h | 1.139 | 1.129 |  |  |  |  | 30 |  |  | g | 2020-12-21 | 2021-02-03
|  |  | 2 | 1.141 | UCB fabs 3 arrays |  |  | 1.130 | [5 empty] | 25 |  |  | 2 | 2020-06-15 | 2020-07-17
|  |  | 2 | 1.142 | 3 sets of lenslet wafers fabricated |  |  | 1.134 | [5 empty] | 40 |  |  | 1 | 2021-01-22 | 2021-03-19
|  |  | 2 | 1.143 | Assemble 3 UCB UFMs w/ J4-J6 | Bbonder |  | 1.141 | 1.92 | 1.135 | 1.142 |  |  | 3.5 |  |  | 3 | 2021-03-22 | 2021-03-24
|  |  | 2 | 1.144 | Test 3 UFMs in DR3 |  |  | 1.143 | 1.133 |  |  |  |  | 30 |  |  | o | 2021-03-25 | 2021-05-10
|  |  | 2 | 1.145 | NIST fabs 3 arrays |  |  | 1.137 | [5 empty] | 40 |  |  |  | 2020-05-06 | 2020-07-01
|  |  | 2 | 1.146 | 3 MF horns fab/shipped to Princeton |  |  | 1.138 | [5 empty] | 30 |  |  | 4 | 2020-05-06 | 2020-06-17
|  |  | 2 | 1.147 | Assemble 3 UFMs w/ K1-K3 | Lbonder |  | 1.145 | 1.107 | 1.139 | 1.146 |  |  | 10 |  |  | k | 2021-01-27 | 2021-02-09
|  |  | 2 | 1.148 | Test 3 UFMs in DR2 |  | 12 MF-h | 1.147 | 1.140 |  |  |  |  | 25 |  |  | g | 2021-02-10 | 2021-03-17
|  |  | 2 | 1.149 | NIST fabs 3 arrays |  |  | 1.145 | [5 empty] | 40 |  |  |  | 2020-07-02 | 2020-08-27
|  |  | 2 | 1.150 | 3 MF horns fab/shipped to Princeton |  |  | 1.146 | [5 empty] | 30 |  |  | 4 | 2020-06-18 | 2020-07-29
|  |  | 2 | 1.151 | Assemble 3 UFMs w/ K4-K6 | Lbonder |  | 1.149 | 1.108 | 1.147 | 1.150 |  |  | 10 |  |  | k | 2021-02-10 | 2021-02-24
|  |  | 2 | 1.152 | Test 3 UFMs in DR2 |  | 15 MF-h | 1.151 | 1.148 |  |  |  |  | 25 |  |  | g | 2021-03-18 | 2021-04-23
|  |  | 2 | 1.153 | NIST fabs 3 arrays |  |  | 1.149 | [5 empty] | 40 |  |  |  | 2020-08-28 | 2020-10-27
|  |  | 2 | 1.154 | 3 MF horns fab/shipped to Princeton |  |  | 1.150 | [5 empty] | 30 |  |  | 4 | 2020-07-30 | 2020-09-14
|  |  | 2 | 1.155 | Assemble 3 UFMs w/ L1-L3 | Lbonder |  | 1.153 | 1.151 | 1.112 | 1.154 |  |  | 10 |  |  | k | 2021-03-05 | 2021-03-18
|  |  | 2 | 1.156 | Test 3 UFMs in DR1 | SAT3 | 18 MF-h | 1.155 | 1.148 |  |  |  |  | 25 |  |  | p | 2021-03-19 | 2021-04-26
Formulas:
Monthly = IF(N12<>"",N12,IF([Display:]=" - "," - ",IF(O12<>"",WORKDAY.INTL([Display:],O12-1,weekend,holidays),[Display:]+MAX(P12,1)-1)))
Show Weekends (Daily view only)
Note on E6: Project Start Date Enter the Start Date for the Project. Avoid choosing a date that falls on a Saturday or Sunday.
Note on S6: Daily / Weekly / Monthly: Use this to change the gantt chart view to Weekly or Monthly if you want to see a larger range of dates. Note that the monthly view results in a loss of detail.
Note on S7: Display Week / Display Month: Use this to change the starting week or month shown in the gantt chart.
Note on E8: Today's Date: Use the formula =TODAY() to make the red line in the gantt chart display the current day, or enter the date manually.
Note on D9: WBS Level: Choose the WBS (Work Breakdown Structure) level from the drop-down in this column.
Note on E9: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to automatically update the numbering.
Note on F9: Task Description Enter the name of each task and sub-task. The task description is automatically indented using conditional formatting based on the WBS Level column.
Note on G9: Task Lead Enter the name of the Task Lead in this column.
Note on I9: Predecessor Tasks: You may use this column to calculate the start date for the task based on the end date of the Predecessor you reference. Use a formula like =A13 to reference the WBS of the Predecessor task that must be completed before this task can start. You can also enter the WBS as a text value by entering an apostrophe before the number like '2.3. Avoid circular references, such as choosing the current task as its own Predecessor. Using this column assumes that you want the task to start on the next work day. See the Help worksheet for more examples of using formulas to create task dependencies.
Note on M9: Start Date You can manually enter the Start date for each task, use the Predecessor column to have a Start date calculated automatically, or use a formula to create a dependency on some other cell. See the Help worksheet for examples of creating dependencies.
Note on N9: End Date If you want to define the End date instead of calculating what it should be, enter the date in this column. Otherwise, enter a value in the Work Days or Calendar Days column to define the duration of the task.
Note on O9: Work Days Enter the number of Work Days that you estimate this task will require to complete. Work Days exclude the weekend (defined in the Help worksheet) and the holidays listed in the Holidays worksheet.
Note on P9: Duration: Calendar Days If you want to enter the number of calendar days instead of the number of work days, enter a value in this column.
Note on Q9: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on R9: Color (Optional): Enter a color code in this column to change the color of the incomplete portion of the gantt chart. 1 - 6 = theme-based accent colors k = black r = red o = orange y = yellow p = purple g = green
Note on S9: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1,holidays) to set the Start date to the next work day (excluding weekends and holidays), where enddate is the cell reference for the End date of the Predecessor task.
Note on T9: End Date The WORKDAY() function is used to calculate the ending date so that the End Date does not fall on a weekend or a holiday. If you choose to use the Duration as the input, the End date is calculated as the Start date + Duration - 1.
Note on U9: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on V9: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on W9: Calendar Days Complete [ You can hide this column prior to printing ] This column is calculated by multiplying the Work Days by the %Complete and using the WORKDAY() function to determine how many calendar days have been completed. Note: The conditional formatting used to create the gantt chart references this column.
Note on X9: Calendar Days Remaining [ You can hide this column prior to printing ] This column is calculated by subtracting the Days Complete from the Duration.
Note on Y9: Planned Start & End After creating the project schedule, you can copy the Start and End columns and use Paste Special > Values to paste the dates into the Planned Start and Planned End columns. The planned periods will be represented in the gantt chart using cross-hatching.